## Sheet1
Recommendation | Project title | iWG status | To do item/status | Portal page status | Description | Does site need an update
Edu005 | Sustainability Scholars Program - Returned | Returned | Gillen responded with clarification on 6/10. The iWG should discuss this and decide steps to move forward. | Returned |  | No
Edu004 | Edu004 Sustainability Unit in ENG100 - Submitted | Submitted | schedule a call with COE in fall 2020- MKM had initial conversation with Gretchen to potentially implement in future semesters. | Submitted
Edu003 | Edu003 Sustainability Career Fair - Submitted | Transmitted | Director of Career Services, Jennifer Neef, found that "eco-tagging" may not be the best option. Instead, we can discuss sustainability networking or other options to still provide sustainable career opportunities for students. | Transmitted | The Career Center should work with College of Engineering, College of ACES, and College of Business to incorporate "eco-tagging" in the existing career fairs, as described in the SWATeams' recommendation for Year 1. | No
Edu002 | Edu002 Internship Coordinator - Submitted | Submitted | Resilience and Education SWATeams were copied in an email on 8/2. MKM will schedule a meeting in fall with these groups to discuss this recommendation. | Submitted
Edu001 | Edu001 Environmental Leadership Program - Submitted | Successful |  | Successful | The iWG encourages iSEE to find a donor to support the long-term costs of their proposed Environmental Leadership Program. | No
Res001 | Res001 Champaign County Multi-Jurisdictional Hazard Mitigation Plan - Submitted | Submitted - to route | Bob Flider said to talk to Mike D. first, so Morgan is working on that. - Mohamed said to send it to Mike, chancellor jones, and bob flider when it is ready to sign, rather than making it two separate emails. | Submitted | Chancellor Jones should formally approve the upcoming Champaign County Hazard Mitigation Plan, by signing the document.
LW001 | LW001 Data Repository - Submitted | Submitted | Ximing will seek potential faculty member to lead this effort - emailed Land and Water SWATeam 6/17 | Submitted
Energy004 | Energy004 Energy Conservation Funding - Submitted | Submitted | Morgan spoke with Josh Whitson on 6/11 and he is preparing this information to share with the iWG in the fall - planning to include them in the November meeting | Submitted
Energy003 | Energy003 Energy Master Plan - Submitted | Submitted | need to let SWATeam know that we are holding this during the work on the iCAP 2020 - Morgan will let them know, with the email about Energy004 and Josh's info | Submitted
Energy002 | Energy002 Building Envelope - Successful | Successful | F&S submitted a request to the Student Sustainability Committee, seeking their support to run this pilot project. F&S initiated a meeting with Bill Rose and several F&S team members to discuss first steps. | Successful | F&S should seek funding to pilot the Building Envelope Testing, as recommended by the SWATeam. The selected test buildings should be carefully considered and possibly replaced by other buildings, if warranted. | No
Energy001 | Energy001 Anaerobic Digester Feasibility Study - Submitted | Submitted - to route | Sent to iWG for comments 6/16 | Submitted | ACES should identify a lead faculty member who can coordinate with the iWG to scope and implement a feasibility study. Partial funding for this study could be requested from the Student Sustainability Committe, through their funding application process.
Trans013 | Trans013 UI Ride Survey - Submitted | Successful | iCAP Portal has been updated: Mohamed said that F&S will contact the Transportation SWATeam in the fall to discuss specifics. | Successful | F&S should collaborate with the Transportation SWATeam to complete the survey, once social distancing restrictions are lifted. The survey should include questions related to health/quarantine/safety. | No
Trans012 | Trans012 Carpool Survey - Submitted | Submitted - to return | Ximing to email Yanfeng about this, and let the SWATeam know - this is different from the Campus as a Living Lab (CALL) iSEE seed funding program - back to the iWG to discuss | Submitted
ZW001 | Student Sustainability Ambassador Program - Successful | Successful | Discuss at iSEE management meeting on 10/13. There is a possibility that Eric Green and Meredith Moore will co-instruct this course in spring 2021. | Successful | iSEE should develop a pilot of this class (possibly in NRES or ENVS), and identify a long-term strategy for establishing it as a recurring course. | No