## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | High Resolution Temperature Profiling and Thermal Analysis for Geothermal Energy Alternatives
Total Amount Requested from SSC: | 72977
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Order and purchase field supplies and cables | 8 |  | 2016-09-30
Initiating webpage or mobile app development | 1 |  | 2016-09-30
Installation of FO-DTS with geothermal heat exchanger | 1 |  | 2016-10-15
Drilling, core recovery/description, downhole geophysics | 2 |  | 2016-10-31
Installation of FO-DTS with geothermal heat exchanger | 4 |  | 2016-11-30
Field geothermal exchange test & thermal property test | 8 |  | 2016-12-31
FO-DTS measurement and calibration | 40 and continute |  | 2016-07-31
Optimal cost analysis on loop design and installation | 8 |  | 2016-04-30
Beta test on webpage or app development | 2 |  | 2016-03-30
Online test on webpage or apps | 2 |  | 2016-06-30
Conclude study and submit final report | 8 |  | 2016-07-31
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
DTS enclosure and mounting hardware | 720 | 1 | 720
Solar panel, battery and hardware | 875 | 1 | 875
Cellular modem and accessories | 960 | 1 | 960
DTS Wi-Fi module and accessories | 200 | 1 | 200
Drilling rate per day | 2950 | 5 | 14750
Heat exchange loop and FO cable installation per day | 2950 | 2 | 5900
Geophysic Logging per meter | 16.5 | 100 | 1650
0
0
0
|  | Subtotal | 25055
Publicity & Communication
Cellular data cummnication | 30 | 12 | 360
Publication fee | 750 | 1 | 750
0
0
0
0
0
0
0
0
|  | Subtotal | 1110
Personnel & Wages
U of I student in engineering major (e.g., CEE) | 15 | 640 | 9600
U of I student in science major (e.g., NRES) | 15 | 640 | 9600
UW graduate student in 25% RA per month | 1718 | 9 | 15462
UW Tuition Remisssion for 25% RA per semester | 3000 | 2 | 6000
UW summer salary for Dr. Hart | 1500 | 1 | 1500
0
0
0
0
0
0
|  | Subtotal | 42162
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Travel for UW team and equipment to Urbana field site | 150 | 5 | 750
Travel for U of I team and core sample to UW thermal lab | 300 | 8 | 2400
UW thermal lab supplies | 1500 | 1 | 1500
0
0
0
0
0
0
0
|  | Subtotal | 4650
|  | TOTAL BUDGET | 72977
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
The service time of the team members at the ISGS and the Energy Farm will be in-kind. Support letters are attached.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
The proposed project will collect data over an entire calendar year to identify impacts of seasonal heating and cooling on the subsurface. The outcomes can be used to evaluate geothermal energy contribution for future energy planning on campus. An example figure of energy saved from Buttonfield Elementary School in Champaign is attached.
End of Application