## export 1
The project approval budget was the original scope of work proposed for the project given to us by the architect and engineering firm. The current budget column is the project
as defined by the facility manager within facilities and services including the $8,246 needed to redesign the project for location on the western edge of the ARC roof.
The proposed budget column is the revised estimate including omissions by the architect on the first redesign of the project.
This is the current proposed construction budget for the project reflecting the requested funds from SSC.
Project Budget: ARC - INSTALL SOLAR HOT WATER SYSTEM (U11067) (Sub-project of AUXILIARY FACILITIES SYSTEM R&R FY12 MASTER (U11058))
Budget Code | Description | Project Approval Budget | Current Budget | Proposed Budget | Forecast Amount | Future Contracts
10000 | CONSTRUCTION | 0 | 0 | 0 | 0 | 0
10001 | LUMP SUM CONSTRUCTION | 235000 | 0 | 0 | 0 | 0
10600 | GENERAL WORK | 0 | 38025 | 293003 | 0 | 0
12200 | PLUMBING WORK | 0 | 0 | 0 | 0 | 0
12320 | PIPING/HEATING WORK | 0 | 174008.31 |  | 0 | 0
12600 | ELECTRICAL WORK | 0 | 13162.5 |  | 0 | 0
19020 | BIDDING CONTINGENCY | 11750 | 11750 | 14650.15 | 0 | 0
19030 | CONSTRUCTION CONTINGENCY | 23500 | 23500 | 29300.3 | 0 | 0
19040 | RESERVE | 0 | 8100.19 |  | 0 | 0
Category Total: |  | 270250 | 268546 | 336953.45 | 0 | 0
20000 | FURNITURE, FIXTURES, & EQUIPMENT | 0 | 0 | 0 | 0 | 0
Category Total: |  | 0 | 0 | 0 | 0 | 0
30000 | OWNER'S COST | 0 | 0 | 0 | 0 | 0
30400 | FM ASSISTS/SYSTEMS INTEGRITY | 1175 | 1175 | 1176.72 | 0 | 0
30700 | PROJECT MANAGEMENT FEE | 11183 | 11084 | 13605.94 | 10804 | 10804
30720 | COMMISSIONING AND INSPECTION | 3525 | 3525 | 4395.045 | 3525 | 3525
Category Total: |  | 15883 | 15784 | 19177.705 | 14329 | 14329
40000 | PROFESSIONAL SERVICES | 33367 | 0 | 0 | 0 | 0
41200 | A/E SCHEMATIC DESIGN | 0 | 0 | 0 | 0 | 0
41300 | A/E DESIGN DEVELOPMENT | 0 | 16048 | 16048 | 16048 | 16048
41400 | A/E CONSTRUCTION DOCUMENTS | 0 | 10340 | 10340 | 16048 | 16048
41500 | A/E BIDDING | 0 | 1292 | 4092 | 1292 | 1292
41600 | A/E CONSTRUCTION ADMINISTRATION | 0 | 5170 | 5170 | 0 | 0
41650 | A/E CONSTRUCTION ON-SITE OBSERV. | 0 | 3000 | 3000 | 0 | 0
41700 | A/E POST CONSTRUCTION / WARRANTY | 0 | 0 | 0 | 0 | 0
41900 | A/E REIMBURSABLES | 0 | 3000 | 3000 | 3000 | 3000
41950 | A/E OTHER SUPPLEMENTAL SERVICES | 0 | 4566 | 4566 | 4556 | 4556
Category Total: |  | 33367 | 43416 | 46216 | 40944 | 40944
GRAND TOTAL: |  | 319500 | 327746 | 402347.155 | 55273 | 55273
Unallocated Funds: |  | 8246 | 0 | -74601.155 | 272473
Notes
9/2/11 Budget Version 5: SD/DD Estimate
General = $67,275
Plumbing = $153,208 (assign to General)
Total = $220,482
FAC = $235,000
PM Fee lowered b/c it was incorrectly high.
Remaining funding in Reserve.
2/27/12 Budget Version 7: SD/DD Estimate REVISED
Total SD/DD Estimate = $205,611
FAC = $235,000
Construction contingency updated to reflect 10% of the FAC.
Remaining funding in Reserve.
4/9/12 Budget Version 8: 95% CD Estimate
Total 95% CD estimate = $225,195
FAC = 235,000
Remaining funding is in Reserve