## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Large scale implementation of E2E Paradigm for Food Waste to Biofuel and Biomaterial
Total Amount Requested from SSC: | 200000
Amount Requested as: |  | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Establish pretreatment methods | 8 weeks |  | May, 2018 - July, 2018
Upgrade the system to operate with this feedftock | 8 weeks |  | July, 2018 - September, 2018
Convert food waste with the system | First run period -- 8 weeks, continuely run after that |  | September, 2018 - March, 2020
Test oil yeild and quality | First test -- 8 weeks, continuely test after that |  | November, 2018 - March, 2020
Economic analysis of the system | 16 weeks |  | Janary, 2019 - May, 2019
Upgrading of the bio-crude oil and bio-material | Method investigation -- 8 weeks, continuely after that |  | Janary, 2019 - March, 2020
Implementaion of product in realy life | 24 weeks |  | September, 2019 - March, 2020
Final report write up | 8 weeks |  | March, 2020 - May, 2020
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Equipment rental (including HTL pilot reactor, and water) | 30000 | 1 | 30000
HTL system renovation | 35000 | 1 | 35000
0
0
0
0
0
0
0
0
|  | Subtotal | 65000
Publicity & Communication
Workshops | 1000 | 2 | 2000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 2000
Personnel & Wages
Graduate students | 15 | 3200 | 48000
Undergraduate students (including webmaster) | 10 | 3000 | 30000
0
0
0
0
0
0
0
0
|  | Subtotal | 78000
Project Budget per F&S
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Laboratory testing supplies | 25000 | 1 | 25000
Analysis (feedstocks characterization, biocrude, upgrading ) | 25000 | 1 | 25000
Miscillanouse | 1000 | 1 | 1000
Student travel (4 person-trips) | 4000 | 1 | 4000
0
0
0
0
0
0
|  | Subtotal | 55000
|  | TOTAL BUDGET | 200000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
The PI has Obtained aConference grant from NSF INFEWS program ($50,000) to hold a Workshop June 13-15, 2018. The team is preparing a proposal (total $2.5 million) for the INFEWS Program Track #2.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
The pilot HTL reactor is capable of processing two ton of wetwaste (20% solids), with a carbon capture efficiency of 70%, which convert 130 kg of carbon in the biowaste into a carbon neutral biocrude oil . This capacity will translate into a reduction of 426 kg/day, or 156 ton per year, of carbon dioxide emission.
End of Application