## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Implementation of Heating/Cooling Unit in Bus Stops via Off Grid Solar Energy System
Total Amount Requested from SSC: | 9175
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Purchase necessary Items | 1 |  | Late January
Estimated Lead Time on Materials | 4 |  | Late February
Construction of Units | 0.5 |  | Early March
Quality Assurance Testing | 1 |  | Mid March
Regular Operation | - |  | -
Final Report | - |  | Early May
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Space Heaters 1500W | 53.94 | 4 | 215.76
Solar Panel 280 W | 249.99 | 8 | 1999.92
Panel Structure | 340.59 | 4 | 1362.36
In-Line fuse 15A | 17.49 | 8 | 139.92
Charge Controller | 19.99 | 4 | 79.96
Renogy 12V 160Ah Battery | 314.99 | 4 | 1259.96
ANL Fuse | 17.99 | 8 | 143.92
Inverter 2000W | 139.99 | 4 | 559.96
Battery Enclosure | 340 | 4 | 1360
Water Protected Surge protector | 17.99 | 4 | 71.96
MMF and FFM Connector | 12.99 | 4 | 51.96
Oscilating Fan | 33.95 | 4 | 135.8
Time adjuster electronics | 100 | 4 | 400
Metal Support Rod | 69.99 | 8 | 559.92
|  | Subtotal | 8341.4
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Electrician | 30 | 20 | 600
Labor | 10 | 15 | 150
0
0
0
0
0
0
0
0
|  | Subtotal | 750
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 9091.4
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
This project will generate 970 kWh per year, which corresponds to 1,621 lb of CO2 per year.
End of Application