## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Sustainable Dance Floor at the Illini Union
Total Amount Requested from SSC: | 10409.71
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Identify suitable location at the Illini Union | 1 |  | 2017-10-05
Determine size and quantity of raw materials | 2 |  | 2017-10-12
Purchase equipment and materials | 4 |  | 2017-10-25
Start of project construction | 6 |  | 2017-10-30
Hire expert personnel to set up wiring and floor | 6 |  | 2017-10-30
Testing | 9 |  | 2017-11-14
Testing with students | 11 |  | 2017-11-30
Battery performance tests | 11 |  | 2017-11-30
Publicity on social media | 11 |  | 2017-11-30
Target completion date | 12 |  | 2017-12-05
Final Report | 14 |  | 2017-12-20
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
PZT crystals(StemINC(` | 5.89 | 600 | 3534
Compression spring(small) | 0.8625 | 600 | 517.5
Compression spring(large) | 3.45 | 144 | 496.8
Rubber mats | 55 | 24 | 1320
Bridge rectifier circuit and OP amps | 2.142 | 24 | 51.408
Connecting wires | 15 | 14 | 210
Energy meter | 200 | 1 | 200
Li-ion storage battery | 200 | 1 | 200
Spot lights | 50 | 2 | 100
Arduino microcontroller | 30 | 1 | 30
Music system | 250 | 1 | 250
|  | Subtotal | 6909.708
Publicity & Communication
Posters , flyers at the union | 5 | 20 | 100
Social media | 0 |  | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 100
Personnel & Wages
Labour for transport |  |  | 200
Installation and wiring |  |  | 1500
Lighting and sound system |  |  | 200
0
0
0
0
0
0
0
|  | Subtotal | 1900
Project Budget per F&S
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
T shirts, goodies for participants |  |  | 500
Budget Tolerance at 10% |  |  | 1000
0
0
0
0
0
0
0
0
|  | Subtotal | 1500
|  | TOTAL BUDGET | 10409.708
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
End of Application