## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Food Processing Plant – Hand Wash Sink Replacement
Total Amount Requested from SSC: | 10450
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Procure Hand Wash | 6 weeks |  | Feb. 2018
Install Hand Wash | 2 weeks |  | Mar. 2018
Begin Using Hand Wash | - |  | Mar. 2018
Design & Build "Water Saved Display" (if desired) | 4 weeks |  | Apr. 2018
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Hand Wash System | 8200 | 1 | 8200
Utility Installation | 1500 | 1 | 1500
"Water Saved Display" (if desired) | 750 | 1 | 750
0
0
0
0
0
0
0
|  | Subtotal | 10450
Publicity & Communication
Covered by FSHN Department |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 10450
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
N/A
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
N/A
End of Application