Please submit this completed application and any relevant supporting documentation by the deadline listed on the SSC website to Sustainability-Committee@Illinois.edu.The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC at Sustainability-Committee@Illinois.edu.

# General Information

Project Name: Pollinator Awareness Signage

Total Amount Requested from SSC: $3000

Project Topic Area(s):	☐Energy	☒Education	☐Food & Waste

☒Land		☐Water	☐Transportation

# Contact Information

Applicant Name:  	Rachel Daughtridge

Unit/Department: 	Student, College of ACES

Email Address:	 	dghtrdg2@illinois.edu

Phone Number: 	513-546-9609

Project Team

| Name | Department | Email |
| --- | --- | --- |
| Name | Department/Organization | Email Address |
| Name | Department/Organization | Email Address |
| Name | Department/Organization | Email Address |
| Name | Department/Organization | Email Address |

# Project Information

Please provide a brief background of the project, the goals, and the desired outcomes:

The goal of my project is to provide awareness about pollinators around the University of Illinois (UC) campus. I intend to do so with signage inside and outside of campus buildings, giving facts about native plants and pollinators. This signage will be approved by the University Board.

Please provide a brief summary of how students will be involved in the project:

Approximately 2-3 other students will be assisting me with the design and posting of signage.

Please provide a brief summary of the project timeline:

From now until the end of February, I plan to work with 2-3 other students to design a series of approved signs. Once approved, we will submit print orders for these posters to be finished by mid-March. Beginning in April, we will post signage around popular areas on campus, and near native plant plots.

Additional comments

This project will bring our university one step closer to being certified with Bee Campus USA, a movement set on promoting pollinator awareness.