Land and Water SWATeam Meeting

Date: September 26, 2019

Time: 4-5 pm

Members in attendance: Meredith Moore (iSEE), Morgan White (F&S), Ximing Cai (iSEE), Reid Christianson (Faculty, Co-chair), Allen Parish (Staff), Bruce Branham (Faculty), Brent Lewis (Staff), Eliana Brown (Staff), Jamie Ellis (Staff), Claire Samojedny (Student), Vikram Muthuvel (Student), Ella Liskiewicz (Student), Valerie Ramirez (Clerk)

Meeting

- Introductions

- iCAP 2020 Timeline

  - Need team draft objectives by the end of October and send to iCAP Working Group

    - Campus Sustainability Celebration on October 23rd

      - Receive public input and opinions on iCAP 2020

  - Make changes to draft in November to include feedback

  - Will have a writer to write objectives in December/January

  - Get input form the public and tweak objectives in February/March

  - Have a solid final draft that Sustainability Council can review in April

  - Resolve issues with decision makers during in the summer

  - Goal: Formally approve 2020 iCAP in the fall

- iCAP Objectives

  - What should be our key priorities for the next 5 years?

    - Objectives: what do we want to accomplish?

  - Refer 2015 iCAP chapter of water and land for reference of past objectives

    - Some objectives have been met and some have not been met

    - Use 2015 objectives as information we can use for creating new objectives

      - Know where we are and where we want to go

    - New ideas are encouraged, not just reworking old ones

  - Objectives should be measurable, actionable, and achievable with dates and specificity

    - Can include dates earlier than 2020 or extended dates

  - Don’t worry about terminology

  - Come up with ideas to discuss at next meeting

- Team Recommendations

  - Can still work on past/new recommendations if team decides aside from the iCAP objectives

  - Brent Lewis: focus on water issues on campus

    - Idea for all new buildings to have new pipes that allow for reusing water

      - Can be part of iCAP objectives

- Recommendation updates

  - VetMed Parking

    - Reduce runoff that floods into the Dairy Farm

      - Transmitted and waiting for response

  - Agroforestry

    - Increasing trees campus-wide and along Embarras River

      - Transmitted and successful

      - ACES will continue to discuss it and Brent will be drafting some comments

  - Lot F4

    - Stalled but still on list

  - Lot F23

    - Implement green storm water and monitor and quantify runoff from parking lot

      - Art Schmidt possibly is working on Lot F23

  - SeeClickFix

    - Tracking system at F&S so submit issues on infrastructure

    - F&S said yes

  - Recently sent recommendation

    - Tree canopy cover as a resilient landscape strategy

- Assignments

  - Think of ideas for objectives for next meeting