Zero Waste SWATeam: Objectives Review and iWG Feedback

Food Waste Management

Reducing Food Waste

1. 	By the end of FY2021, launch a marketing strategy that informs everyone on campus about: (a) resources needed to produce food of different sorts, (b) GHG emissions from producing these different food types, (c) costs and realities of food waste disposal, (d) GHG emissions from food decomposition in landfills, and (e) suggestions for decreasing food waste. This will include continuous research on strategies in collaboration with the nutrition team within Dining Services, e.g., use employee-operated salad making stations instead of an open salad bar.

- How would this be implemented?

  - Using digital media (Instagram/Reddit/Facebook pages), digital screens, posters, advertisements, etc, the information above would be distributed to as many campus units as possible. Possible targets include dining & housing, Bevier café, buses/transit, etc.

  - This strategy has the campaign that Oatly, an oat milk brand, has launched with catchy advertisements that appeal to the younger generation.

- Which Unit/Department would implement this?

  - This could begin as a pilot program with dining and housing, but with proven results, would expand to a broader scope.

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic)?

  - Thurman and Kelly will ask marketing department ballpark cost

- Who would pay this cost?

  - For advertisements in Dining and housing, they would pay the cost.

  - For other units, the content would be distributed at no cost, but other units would likely pay the costs to distribute (printing materials and obtaining supplies, for example).

- Potential Project Ideas?

  - Launch a weekly food waste competition/challenge.

  - Use bus advertisements to create appealing content.

- Response to iWG Feedback:

  - (MW) RFW1: Students want meatless Mondays in dining halls, veggie experiment day to encourage plant-based diets.

    - There was a vegetarian dinner served every Wednesday night in LAR dining hall for quite a few years until it was discontinued. Would like to see it return in ways like this in ALL dining halls.

2. 	By the end of SP2021, all self-operated campus food services will track and submit food waste numbers.

- What does self-operated food Services mean?

  - This means that the unit will produce their own food supply, and it is not contracted out to third party sellers (Ex: Illini Union restaurants).

- How would this be implemented?

  - For Self-Operated units: Both pre and post-consumer food waste is pictured, weighed, and submitted to a specific program (Dining uses Spark for post-consumer, LeanPath 360 measures pre-consumer waste). Both should be measured.

  - The staff who would be in charge of measuring the waste must be trained properly on how to improve food waste numbers. This is integral to the success of this objective.

  - This information would have a page on the iCAP Portal, including Dining’s current numbers.

  - Moved to Purchasing: for contracted units, new or renewed contracts would include stipulations for tracking food waste. These stipulations would have to be modified to conform to the grab-and-go style of many of these contracted units.

    - Mandate recycling requirements.

    - Mandate more sustainable supplies (aluminum foil substituted for plastic wrap, no Styrofoam, etc.)

    - Mandate that all garbage must be paid for by the individual unit.

- Which Unit/Department would implement this?

  - Self-Operated: Housing/Dining, Bevier Café, Catering, institute cafes (ex: Beckman, IGB, Lincoln Hall), and coffee shops.

  - Move to Purchasing: Concession/Contracted: Athletics, Illini Union.

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic)?

  - For Dining, the infrastructure is already set up, so the cost would be low.

  - For other entities which do not already utilize food waste measurements, the cost would be higher.

- Who would pay this cost?

  - Each unit would pay its own cost.

- Potential Project Ideas?

  - Publicize the food waste generated (1/3 lb per meal).

- Response to iWG Feedback

  - (JK) RFW2: What is the definition of “all campus food services?”

    - All foodservices operated by the university directly. Examples would be University Housing Dining and Catering, the café at Beckman institute, the kiosk at the Law school and Spice Box at Bevier Hall. All contract foodservices utilizing University space or events would be encouraged and possibly contractually compelled in the future to comply with University Policies.

3. 	By the end of SP2021, a campus wide Food Donation webpage should be created, implemented, and publicized by appropriate affiliates to donate excess food instead of disposal.

- How would this be implemented?

  - Dining already collaborates with a non-profit who distribute excess food from dining halls to those in need. This program would have to be redefined to accommodate an internal, broader system.

    - One barrier is connection to those who are picking up the food, who are often older volunteers or lack transportation means.

      - Volunteer runners might be a way to resolve this issue.

- Which Unit/Department would implement this?

  - Private food services (Restaurants, cafes, coffee shops, etc)

  - Miscellaneous Campus Units: Krannert, Bevier, IGB, etc.

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic)?

  - If a CS student/class would utilize this project idea as an opportunity, then there would be very little cost to this in terms of overhead.

  - Broadcasting this program to available units might have a larger associated cost.

- Who would pay this cost?

  - Unsure.

- Potential Project Ideas?

  - N/A

- Response to iWG Response:

Diverting Food Waste

- By the end of FY22, develop a comprehensive plan to sustainably dispose of food waste, e.g., create a large-scale anaerobic digester and increase composting.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

2. 	By the end of SP21, recycle all used cooking oil into biodiesel or some other beneficial use.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

Education

Communication, education, promotion, daily operating instructions, and campus expectations are cornerstones of achieving a Zero Waste Campus and objectives are detailed below.

- By the end of FY20, Sustainability Ethics Training will be incorporated as a part of annual faculty and staff ethics training.

- How would this be implemented?

  - In cooperation with the Ethics Office

- Which Unit/Department would implement this?

  - iSEE with the Ethics Office

- Why does this objective need to be implemented by the date stated?

  - It needs to be done ASAP, as this training is only done once a year.

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

  - Little to none, other than content creation (~$500-1000).

- Who would pay this cost?

  - iSEE/SSC, since the media lab is under iSEE. The SSC would likely only fund this project is the content was made available to students; since the SWATeam is seriously considering seeking student sustainability ethics training, this is possible.

- Potential Project Ideas?

  - See above.

  - Use media lab to create content for relevant sustainability topics.

- Response to iWG Feedback:

2. 	By the end of FY20, information on the Zero Waste Program should be communicated to everyone on campus and included in all campus/student orientation programs and classes. All new students will receive sustainability education, e.g., in a LAS 101 type course or online training. New Residence Hall Packages and/or Video should explain how and where to recycle and information about what items are recyclable in dorms and on-campus; personalize each student packet with a note from the Chancellor welcoming the resident and encouraging “Reduce, Reuse, and Recycle” to achieve a zero-waste campus by 2030. Note that daily campus waste equates to about 1 lbs of solid waste per student per day.

- How would this be implemented?

  - The details will be worked out by parties involved (See below); generally, this will be implemented in freshman orientation courses and residence halls as detailed in the objective.

- Which Unit/Department would implement this?

  - There are many parties involved in this objective, so a cooperative venture between the education component of iSEE (both SWATeam and Gillen Wood). The ZW Coordinator should also play a role in implementing this. It may also be worth involving Housing/Dining (access to many data sets, as well as a communications team).

- Why does this objective need to be implemented by the date stated?

  - ASAP, as orientation will only happen once a year (specifically, at the beginning of the year), so it’s important to implement early enough as to not miss a year.

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic)?

  - The content cost ($0 if using content already created) would be little to none, and training and most implementation could be associated with the responsibilities of the ZW Coordinator/Sustainability Programs Coordinator.

- Who would pay this cost?

  - No associated cost.

- Potential Project Ideas?

  - Potentially pursue the addition of a sustainability gen ed category (like behavioral sciences, humanities, NWC, etc); contacting the Student Government Sustainability Committee would be a good place to start.

- Response to iWG Feedback:

  - (SG) E1: This is a good idea but who is going to be responsible for this? Do we need a new staff member? iSEE? Is it uniform across the university or by college?

    - Already being worked on with Ethics and Compliance office and iSEE and will be a prioritized agenda item in the Spring semester.

3. 	Starting FA20, the Chancellor will provide a letter at the beginning of every semester through all available mechanisms to serve as a reminder and update on the campus zero-waste goal, objectives, and progress.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

4. 	By FA20 the university will hold at least one (1) sustainability event each month of the academic year via the Education and Zero Waste SWATeams.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

  - (JM) E4: Will the Education SWATeam run the sustainability events each month? One event per month is not trivial.

    - They can be involved in the events and/or coordinate but I do not think their involvement is a requirement. Additionally, the SSLC could assist or take responsibility for planning and/or implementing these events.

5. 	By FA20 include at least one short informational sustainability message per week in a campus-wide email. (e.g. “There is a campus myth that recyclables are removed from the waste stream. This is not true. Always place your recyclables in the appropriate bin.” Or “Are you aware that placing a coffee cup with some liquid in a recycling bin prevents the entire contents of the bin from being recycled due to contamination?”)

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

  - (JM) E5: One message per week seems excessive; maybe do it once a semester with the chancellor’s email?

    - Do not believe it is excessive as they will be short one or two sentence blurbs.

6. 	By FY21, implement a program to periodically place tent cards in dining halls and coffee and lunchrooms with sustainability content (ex: “Don’t Forget to Recycle,” “Did you know that paper coffee cups cannot be recycled,” etc.).

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

7. 	By FY21, provide mandatory departmental training on zero-waste protocol, such as what to do when emptying an office, handling office materials, such as toner cartridges, office supplies, batteries, and other materials, that are non-routine.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

8. 	By FY21, designate departmental contacts to serve on a campus master list of people with whom the materials management and Zero Waste Coordinator can communicate and educate on proper procedures and updates. Encourage feedback from building occupants regarding zero waste questions, needs, opportunities, ideas, and suggestions.

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

  - (MW) E8: How about a Zero Waste Listserv?

    - Like this idea.

9. 	By FY21, implement regular campus-wide education/promotion/outreach on materials management and zero waste. Examples include competitions, webpage, Facebook page, Twitter, Instagram, Earth Day/America Recycles Day events, art contents using recyclables, reuse workshops, etc.

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

- (SG) E7: Who would provide departmental training?

  - The Zero Waste Contacts (ZWC), appointed by each entity, whether it be a college, department, a building, etc. This ZWC could be a student, staff, faculty, community member, or other responsible individuals who could fill the role.

10. By FY21, create positions for Student Residence Hall Sustainability Coordinators. These Coordinators will educate students on sustainability and find solutions to sustainability issues. A team of Student Coordinators also could work in each residence hall and in other buildings to help coordinate waste reduction.

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

11. By FA21, provide requirements through student affairs for Registered Student Organizations (RSOs) in regard to sustainable regulations for a club to maintain good standing and provide student education opportunities.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

Purchasing

Response to general questions:

- (JK) P: If it “appears unlikely that the campus will meet the 2020 goal of 50% of office paper being purchased with a recycled content of 30%,” then what does this mean for the university? Does anything happen, or do the goals change so that they are achievable?

A new goal was created. Unsure of what this means for the university. I think every 5 years when the iCAPs are being reviewed and revised, the university should put out an official document that states what goals were and were not met. Additionally, the decision is contextual; analysis on why the goal was not met may be required to determine if a revision of the goal is required. It may be an option to enlist the ZW coordinator for contacting departments. Another option is for an oversight committee at the Chancellor/Vice Provost’s office (or in collaboration with iSEE) to determine areas for improvement or action modifications.

1. 	Effective FA20, use reorganized and sustainably prioritized iBuy system for all purchases unless there is a compelling reason to use Banner. Using iBuy will reduce resources, such as paper, ink, and labor for purchasing activities. Include in iBUY energy efficiency information, e.g., Energy Star and EPEAT (Electronic Product Environmental Assessment Tool) for computers and electronics to reduce energy consumption. Include more visible “Sustainability Approved” logos and descriptions, while also moving sustainable (and financially feasible) products to the top of the item lists, such as office paper with recycled content as discussed below.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

2. 	By FY25, all purchases must apply Environmentally Preferable Purchasing (EPP) wherever legally possible (as stipulated by the Procurement code), as specified by the EPA, which is an important step towards achieving a zero-waste campus.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

  - This will contribute to creating a materials management approach for reducing/eliminating products that result in landfill destined waste.

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

- (MW) P2: Provide a link to EPP Purchasing.

  - Environmentally Preferable Purchasing (EPP) is a strategy and policy from the EPA. To learn more about this practice go to:

http://www.epa.gov/epp/pubs/guidance/finalguidance.htm

3. 	By the end of SP21, all purchases are made in accordance with the procurement code. This could involve purchasing units submitting a brief annual report stating that they have followed the procurement code.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

4. 	By the end of SP21, integrate sustainability requirements into campus contracts and competitive bidding for materials and services, as well as concessions. This will encourage suppliers to facilitate achieving a zero-waste campus by favoring products, services, and packaging that: (1) generate zero waste, (2) are durable, built for reuse and repair, (3) are recyclable or compostable at end of life through the vendor, and (4) minimize waste production during usage, e.g., copiers that print double-sided, utilize 100% post-consumer paper, reusable toner bottles/cartridges by the company, aluminum in place of plastic, no Styrofoam, etc.

- How would this be implemented?

  - Aaron Finder (Purchasing) will draft template for contracts stipulating sustainable requirements.

    - This will include contracts for concessions as well as standard office contracts. The materials and services contracts differ from concessions contracts, so the templates will target different standards.

- Which Unit/Department would implement this?

  - Purchasing

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

5. 	By SP21, all campus entities (i.e. colleges, schools, departments, auxiliary units [Ex: Housing/Dining, McKinley, Illini Union, Campus Recreation], etc) should adhere to the SMARTway program (which tracks freight emissions to incentivize sustainable shipping practices).

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

  - (JK) P5: Define all campus units. Also, is there some way to include sororities/fraternities and auxiliary services in the SMARTway program?

    - The phrasing has been revised to all campus entities (i.e. colleges, schools, departments, auxiliary units [Ex: Housing/Dining, McKinley, Illini Union, Campus Recreation], etc). As for the second part, it is more important to establish the SMARTway program within the campus or campus-certified housing. Then, once established, there may be a way to incorporate private entities.

6. By the end of SP21, applicable staff will have been educated on proper sustainability goal metrics, standards, and policies;

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

7. At least 50% of purchases of products like office paper, cleaning products, computers, other electronics, and freight/package delivery services must be sustainable to meet campus standards by FY21, and 75% by FY25, which was included the iCAP 2015.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

8. By FY20, purchase other items and equipment that contain a minimum of 50% post-consumer content as possible.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

9. By FY21, purchase chlorine-free paper made with non-virgin, 100% post-consumer content. How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

Increasing Recycling Rates

- By FY25, eliminate single use plastic sales; replace plastics with single or re-usable aluminum containers in vending and other sales because the recycling market for aluminum remains strong whereas the plastic recycling market has collapsed. In addition, plastic usage is being discouraged because of environmental and ocean impacts. This needs to be implemented in light of the resources required to manufacture, recycle, etc either plastic or aluminum. However, plastic is shifting to cost-based recycling, and is increasingly difficult to find sellers; aluminum is stable and can actually turn a profit from its downcycling.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

  - Switching to a self-serve system (Ex: the machine dispenses the product into a reusable container). Explore commercial composting to allow for the introduction of bioplastics.

- Response to iWG Response:

- By FY20, install Special Collection Boxes for recyclables and Blue (recycling) Bags - Some buildings do not have a separate bin for blue recycling bags so the recycling is included with regular waste and must be hand sorted at the Transfer Station. At locations where there is insufficient space for a large bin, install a smaller bin so the recycling can be picked up by the recycling truck not the waste truck. Create a system for pre-sorting recyclables, including cardboard and aluminum, which are the most marketable commodities. This should include handing each tailgating party a Blue Recycling Bag so the tailgaters can separate their aluminum, cardboard, and plastics from general waste on-site. After the athletic event, the recycling truck will pick-up the blue bags, which can be left near the usual waste containers.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY21, create and distribute a Student and Faculty Transfer Station Video with Statistics – Every day the Transfer Station sends about 55,000 lbs of waste daily to the Danville, IL landfill, which corresponds to about 1 lb/student per day and include photos and video of the process.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY21, create Recycled Art Contest - Students could have access to the recycled materials from the transfer station, e.g., cardboard, aluminum, plastics, newspaper, metal cans, etc., to create an art object or statue from recycled materials to promote recycling in the dorms or dining hall. It is anticipated that iSEE would provide an award for the top three (3) works of art. During the contest, students would be reminded to use recycled paper and biodegradable, earth-friendly glues, paints, pencils, and other supplies.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY22, data from newly instrumented waste trucks that weigh each pick-up should be used to target the top five waste producing buildings and these units should receive “Reduce, Reuse, and Recycle” training.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By SP21, recycling bins will be located everywhere they are needed across campus. In SP21, a vending machine tax will create a fund for supporting the transition to Zero Waste (which can include, but does not need to exclusively pertain to new recycling bins).

- How would this be implemented?

  - This tax would have to work with vendors to ensure that the tax would have to work towards incentivizing students to not use the vending machines, as well as encouraging vendors to minimize and reduce the single-use plastics used in vending machines. One possible issue would be the commission-based profit of the University from the vendors, making the idea of using the funds for zero waste initiatives much more difficult.

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By SP21, when the new recycling bins are available everywhere on campus, all standalone trash cans, deskside waste bins, and trash cans in classrooms will be eliminated. Everyone is to take responsibility for their own waste to achieve a zero-waste campus.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By SP21, encourage reusable lunch bag and containers coupled with separation of food waste to create zero waste lunches.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY20, expand recycling to new materials, e.g., non-rechargeable batteries, glass, wood, electronics, etc.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

- (MW) IRR9: What does “white paper” mean?

  - White paper is virgin paper, and it has been eliminated from this objective as it’s being addressed in other objectives. That said, it may be useful to know this extra information: an authoritative report which used to argue a specific position or propose a solution to a problem, addressing the audience outside of their organization. Today, white papers have become popular marketing tools for organizations especially on the Internet since many potential customers or students search for information on the Web.

- By FY21, ensure recycling of all industrial waste produced on campus, such as, wood, vehicle batteries, scrap metal, wire recycling, concrete, tires, and any other items that have a potential market.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY21, ensure waste diversion opportunities in all campus areas including mail rooms, copy rooms, break rooms, and department kitchens.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

  - (MW) IRR11: What does “ensuring waste diversion opportunities in all campus areas” mean?

Reducing Consumption

- By FY20, reduce paper consumption by editing and proofing electronically. Set all printers and copiers to double-sided printing. Discourage remote printing because 30% of these documents are not collected. Instead encourage “FollowMe Printing”, which makes users activate printing at the printer with a USB drive.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY21, develop system for invoicing campus units for waste, energy, and building usage.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

Increasing Reuse Rates

- By FY21, create Re-Use Stations where old office furniture, phones, staplers, manila folders, pens, pencils, markers, etc., are organized on shelving for selection by future users. When a staff member orders “new” office supply, the purchasing agent and/or staff should check the Re-Use Station before ordering any new items.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY21, create Electronics Re-Use Stations where student owned computers, monitors, printers, and other electronics can be placed and selected by other undergraduate and graduate students for their offices. There is an area in the Civil Engineering Crane Bay where equipment is placed and students can select monitors and printers for their offices.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

  - (MW) IReuseR2: Provide more details about the program within Civil Engineering.

    - In CEE there is an area in the Crane Bay where old/obsolete electronics are placed for disposal. Students have acquired old monitors, printers, keyboards, etc. for their offices. If the items are not claimed, they are wrapped on pallets and shipped out for disposal somewhere.

- Extending the life or usefulness of supplies, furnishings, equipment, and other goods via reuse is preferable to recycling or disposing of those items and materials.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- Purchase durable, repairable, and/or reusable goods in place of disposable goods, when possible.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- Establish incentives and pricing structures for utilizing durables with all campus catered and waived events that include food.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- Ensure that unneeded but reusable supplies, equipment, electronics, and furniture are made available to other University units, local non-profits, and/or State agencies through established means and programs.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- Provide intra-campus communication opportunities for departments to post items for campus purchase prior to placing in any campus re-use exchange including surplus property.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- Establish an inventory and storage location for extra materials generated from campus re-models and new construction to be available for building repairs.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

  - (MW) IReuseRates8: F&S already does this; are there other units which need this?

    - Unsure. This would depend on how F&S does this; is all campus building waste stored, or is it just a select portion of buildings?

- By FY21, opportunities for diversion of personal items such as electronics (i.e. computers, printers, scanners, televisions, etc.), cell phones, textiles, household goods, appliances (e.g. microwaves, in-room refrigerators, fans), furniture and other items that students bring to campus-owned facilities that often get abandoned and fed into the University waste stream will be provided, considering the diversity of the campus population that includes students without personal transportation and international students who might be unfamiliar with local resources (Previous events include Illini Gadget Garage [ISTC, Joy Scrogum] & Makerspace Design Lab [College of Business]).

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

Source reduction

- By FY21, F&S should install hand dryers in place of paper towel dispensers in campus restrooms; default to establishing composting of paper towels if hand dryers are not installed.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY20, require all faculty, staff, students or employees leaving their offices for any length of time or facilitating the last class or meeting of the day, to ensure waste is removed from the room and energy conservation is in place, by turning off lights and other unneeded electronic equipment.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FY20, install refill spouts on all new and needing to be replaced drinking fountains.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Feedback:

- (MW) SR3: This is already a requirement for new and remodeled facilities.  Should we work to install these on existing drinking fountains that would not otherwise be remodeled?

  - Possibly in high use areas. Replacing all fountain spouts wherever possible.

- By FY21, reduce use and purchasing of plastics to the greatest extent possible and eliminate all food service-related Styrofoam products. Also ensure all food ware and other single-use inputs are compostable and compatible with University’s compost processing mechanism.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

Building cleaning and maintenance

- By FY21, reduce the use of chemicals used in cleaning and maintenance/service to the extent practicable, using instead environmentally preferable “green” cleaning and other building maintenance/service chemicals (such as adhesives, finishes, paint, etc…).

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- By FA25, eliminate desk-side collection of waste and recycling by custodial or Zero Waste Program staff in favor of occupants transferring materials to centralized collection locations.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- Ensure replacement items and construction equipment minimize energy consumption, such as: energy-saving light bulbs in all campus exit lights, overhead lights and office lights with options for responsible recovery (such as re-lamping programs and compact fluorescent (CFL) light-bulb recycling); motion activated lights, utilize energy saving equipment such as any power tools, floor waxer, etc.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response:

- Storing overstock usable materials and chemicals for future use and/or disposing of these in a safe manner through recycling or hazardous materials handling.

- How would this be implemented?

- Which Unit/Department would implement this?

- Why does this objective need to be implemented by the date stated?

- What would the estimated cost be (give a ballpark estimate if needed and explain your logic).

- Who would pay this cost?

- Potential Project Ideas?

- Response to iWG Response: