## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | A Living Lab Platform Based on the Campus Instructional Facility (CIF) Geothermal Project
Total Amount Requested from SSC: | $10000 (can be deducted to $9318.16 if necessary)
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date (Estimated from Now)
Building Inofrmation Collection | 12 weeks |  | 2021.02.28
HVAC Model Setup | 10 weeks |  | 2021.05.15
Installation of Temperature Sensors | 4 weeks |  | 2021.06.15
Geothermal HVAC Model Setup | 12 weeks |  | 2021.09.15
Installation of Digital Display Screen | 4 weeks |  | 2021.10.15
Data Transformation (All Finished) | 6 weeks |  | 2021.11.30
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Temperature Sensors (Thermocouple thermometers) | 26.56 | 6 | 159.36
Wall-Mounted Digital Display | 1125 | 1 | 1125
Temperature Data Acquisition Device | 199 | 1 | 199
Installation Cost of Digital Display | 500 | 1 | 500
Digital Signal Wires | 33.7 | 4 | 134.8
0
0
0
0
0
|  | Subtotal | 2118.16
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Research Assistanship for one PHD Student (Deducted from 11 months to 9 months) | 800 | 9 | 7200
0
0
0
0
0
0
0
0
0
|  | Subtotal | 7200
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 9318.16
End of Application