## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Precious Plastics Campus Recycling Hub
Total Amount Requested from SSC: | 40500
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Order Equipment | 1 |  | 2021-01-11
Receive and Assemble equipment | 3 |  | 2021-02-01
Test run equipment | 2 |  | 2021-02-15
Develop training standards and documentation | 1 |  | 2021-02-22
Open access of equipment to campus community members | 1 |  | 2021-03-01
Engage students through Fab Lab media team | 3 |  | 2021-03-22
Gather project statistics | 52 |  | 2022-01-11
Expand collection network | 52 |  | 2022-01-11
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Plastic shredder | 5000 | 1 | 5000
Sheet Press | 2000 | 1 | 2000
Injection Molding Machine | 1500 | 1 | 1500
wall power connections for new machines | 5000 | 1 | 5000
form and mold template material | 1000 | 1 | 1000
Aspire design software | 2000 | 1 | 2000
CNC upgrades for mold making | 5000 | 1 | 5000
Extrusion nozzles and accessories | 1200 | 1 | 1200
storage and collection racks | 2500 | 1 | 2500
Extrusion Machine | 2000 | 1 | 2000
Ipad for data collection | 500 | 1 | 500
safety systems (RFID tool access, ventilation upgrades) | 4000 | 1 | 4000
|  | Subtotal | 31700
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Assemble and test equipment | 20 | 160 | 3200
Develop safety training documentation | 20 | 80 | 1600
Supervise open use time of equipment | 20 | 160 | 3200
Publicty and Engagement | 20 | 40 | 800
0
0
0
0
0
0
|  | Subtotal | 8800
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 40500
End of Application