Sarthak & Avery Meeting Notes

Tuesday, July 27th, 2021

Topic: Commuter Program

- Collaborate with several different departments

  - Veo is a company

  - Justify the point system (ex: Numerical values)

- Program will directly go through parking

  - Ask users to relinquish parking passes, then utilize bus service

- High % of staff lives outside of campus district area

  - Use free parking lots, then take bus

- Parking load is low in parking lots and high traffic areas

- ~17,000 staff

  - Goal: Enroll 100 people by FY24-25, Enroll 500 by FY30

- PRIORITY

  - 1) Primary focus is University incentives through University Stakeholders

  - 2) Third-party organizations and Contracted Groups (such as Veo and Zipcar)

    - Veo membership

    - Campus Bike Center membership

- INSPIRATION: Clean the Air Challenge (Utah)

- Use of QR Code

  - Keep in mind the average age of staff, including technological barriers

- Point System

  - Veo --> Can track number of uses

  - Users can input steps

  - App on phone

    - “I’ve parked outside, now I'm going to bus/hike”

    - Captures number of steps taken or miles traveled

    - Can be difficult on app development individuals

    - Comparisons for App Development (GPS tracking):

      - Safer Illinois – Uses Bluetooth

      - Illini Bus App

  - Point distribution

    - There are not enough bikes on campus available for everyone

    - In order of most to least points awarded:

      - Bike (Veo with more points than personal bikes – still deciding)

      - Walk

      - Bus (easy & readily available to all)

- HR will provide more information about telecommuting (Number of interested and participating staff & faculty)

- Carpooling can be incorporated at a later stage

- ISTC ?? (I had this name written down, but no notes around it)

- Next Steps:

  - Meeting with Sarthak, Morgan, and Stacey to discuss current ideas about the program

  - Meeting with Sarthak, Morga, Stacey, and Avery after preliminary discussion

  - For Avery:

    - Go over the Clean the Air case study, find information and data about our campus that fits the case studies metrics

      - Can find information on iCAP portal, or reach out to Meredith who has information about transportation

    - Send over link to recording & notes to Sarthak