Commuter Program Meeting Notes

Wednesday, August 11th, 2021

Attendees: Stacey DeLorenzo, Sarthak Prasad, Morgan White, Avery Maloto

Parking:

- Similar to what they do for zip car... when you join as a zip car member, you have to get confirmation...

- Ask them to confirm who has a permit

- Need to make sure that people can’t enroll in the Commuter Program, then buy a permit right after

- Record commuter program membership in T2 (their computer system)

- Creating a cross-check system (talk to Maria), to make sure the individual doesn’t have a parking permit anymore before enrolling

- Ask how many current permits are out there for them

- Dual Permits

  - Available to faculty & staff with approval of Campus Services Director and Parking Director (There is no Campus Services Director anymore...)

  - Can be used to park in 2 different lots

Logistics:

- Action Time Line

  - 1) Define who is eligible and what it means to be a commuter

  - 2) Identify and obtain the key players involved in the program

    - Who is from parking?

    - Who is from ____?

    - Project team with roles and contact

  - 3) Identify what platform is going to be used and how the program will be executed

- Take into account the differences in members in the community in defining who is a “commuter”

  - Ex: Someone who lives 5 blocks away vs 10 miles away from campus

- Discuss with Champaign, Urbana, and Savoy to make sure that we aren’t overloading parking??

  - Is this needed??

  - “If you give up your parking space, then _______”

- Give up parking space VERSUS Not having a parking space

  - If you do not have a UIUC Parking Permit, and you are a full-time employee, then you can be a part of the program.

- Target Group: Staff, not faculty

- Scenario: One person has the option to work from home, another does not have the ability to at all.

- Goal: Reward good behavior!

- Start with F&S Staff only, then expand?

  - First come, first serve for a pilot run of the program

  - Can increase the number once the system is modified

- Commuter Program App

  - “Would be a necessary thing” -Sarthak

  - Wellness Center – Sarthak will be reaching out to them to see how they track steps and routes, has a “pedestrian challenge”

    - Bill Sullivan

  - Tracking = Could become a privacy issue, unless they “opt in” to use this feature

  - Who would be the person to first point of contact to create an app?

    - Brad Klein

      - Rockwire [[double check name]]

      - UI Ride

    - Class project?

      - May not be best quality

      - Could take a long time for app dev.

    - Need to be able to say “I need an app that does XYZ”

- Shower Capability

  - Something that was heavily discussed in the TEDTalk

  - Need to know where they are, then you need to have permission from the facility’s manager to be able to utilize the shower

  - Unknown whether or not they facility manager would want to have commuter program members to utilize their facility’s amenities

  - ARC has a shower BUT...

    - You need access [$$ monthly membership] to the ARC

    - Potentially creating a SHOWER ONLY membership to campus rec, that has a “wristband” or another form of proof of membership

      - Does not include access to other amenities, such as pool, gym, etc.

    - Sign-in / Sign-out entry? Contact tracing may include more forms of proof of membership

- Numbers & Other Metrics

  - Do we have the number of full-time employees?

    - DISCLAIMER – I think I got each of these numbers wrong.

    - Headcount Staff: 18,000

    - Academic Staff:...

    - Assistance: 5,706

    - Civil Service: 4,881?

    - Academic Professional: 4,055?

  - Number of current parking permits that are distributed to employees?

  - Number of parking permits available each year to employees?

- Remove all references to students in verbiage

- “Here is our outline of the commuter program...” at the ZTEC (??) meeting (ISTC??)

- How can you earn points?

  - Drop off your car in a parking lot, then earn points by bus, bike, or hike!

  - Concerns with administrative burden

    - What about flat rate rewards for use each year?

    - “If you enroll in the program, we will give you 3 things.”

  - What about “rebates” for individuals who use Zip Car, Veo, or Uber?

- Pete – 2 years ago mentioned UI Emergency Rides for employees. However, there were difficulties regarding restrictions as this would be for personal use.

Next Steps:

- Start with a E-Week survey

  - “We are interested in launching a pilot version of a Commuter Program. If you are interested in participating...”

  - Include questions regarding logistics and benefits for the program to gain community opinion

  - “My Plan Employee Report” from spring, 90 page report

    - “What would it take to give up your car?”

    - \\Fandsu361\TDM\Reports