## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Willard Solar Canopy System
Total Amount Requested from SSC: | 70000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Draft design | 10 |  | Feb 1 2020
Get FAA approval and complete 7460 form | 3 |  | Feb 21 2020
Finalize and review proposals for power purchase agreements | 5 |  | April 1 2020
Finalize design with power partner and get panels/materials on site | 20 |  | September 1 2020
System installation | 16 |  | Feb 1 2021
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
These should largely be covered by solar vendor |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Engineer for system design | 25000 | 1 | 25000
Staff time for design review | 5000 | 1 | 5000
0
0
0
0
0
0
0
0
|  | Subtotal | 30000
General Supplies & Other
Land Surveying | 5000 | 1 | 5000
Project funds for ongoing maintenance, land preparation, potential legal fees | 35000 | 1 | 35000
0
0
0
0
0
0
0
0
|  | Subtotal | 40000
|  | TOTAL BUDGET | 70000
End of Application