## To Do
# | Task | Staff Involved | Deadline | To Do Item per mtg 1/10/12 | Person
1 | Scholarship of Sustainability Series | OS | Feb 2- April, 2012 | working on marketing in January | OS staff
2 | Curriculum Specialist Job desciption | OS& SSC | spring | SSC was supposed to draft mou | McKenzie
3 | formerly known as Prairie Project | OS | spring
4 | Fall 2012 Welcome Week and Sustainability Week early planning | OS | 2012-04-24
5 | Earth Week 2012 Planning | Everyone | 2012-04-16 | set mtg w/talia Osey with SECS | Amy
6 | iCAP Forum at I-Hotel | F&S and OS | 2012-04-16 | start planning what we wanna do | us
7 | Prep for Sustainability Coalition mtg with Chancellor | Morgan, Stephanie | 2012-01-30 | set a mtg with Coalition | MBJ
8 | Energy Liaison presentations at BIF and Krannert | Andy Blacker | spring
9 | Student presentations on small house energy audits | Students/ F&S, SSC | spring
10 | Fund energy improvements in small houses, following small house energy audits | F&S | Summer 2012
11 | CCNet Events w/ OS | OS | third Thursday of each month | invite RCx to the April 19 mtg and send Stephanie the contact people for UBA, Chamber of Commerce, and Eric Jakobssen's folks | mbj
12 | Video for Second Nature award competition | OS | 2012-03-10
13 | Continue working on Solar Farm | F&S | 2012-01-11 | mtg with Purchasing to set when Andy gives me the fact sheet today | mbj
14 | continue working on other Solar projects: rooftops, smart grid, krannert, etc. | F&S, Everyone | 2012-01-13 | draft F&S response to SSC solar proposal for Helen to send | MBJ
15 | Finish getting approval from the Illinois EPA for a biomass permit. | David Wilcoxen | spring
16 | Develop the “Energy Utilities Production and Distribution Master Plan.” | F&S | 2012 calendar year
17 | Develop Pre-proposal document for Chancellor Wise to share with potential donors re: smart campus energy utilities | Barlow Levold | spring
18 | Work with Illinois Biodeisel Initiative to help resolve their concerns | F&S, OS | after 1/31 | sent her scheduling email on 1/19/12 | Amelia
19 | ADA Transition Plan for campus | F&S | 2013
20 | Develop net-zero space increase policy | Helen Coleman, Renee Nagy | spring
21 | Methane Digester at Beef & Sheep facility | Animal Sciences | 2012-01-20 | get some preliminary info | Amelia
22 | Develop ACES goals for 2013 iCAP | ACES, OS | 2012 calendar year | special mtg for 3 of us scheduled on 1/24 | AJN, MBJ, SML
23 | incorporate GHG sequestration from South Farms into campus' GHG inventory | Everyone | 2012 calendar year
24 | Implement changes suggested in True Cost of Water Study | F&S | 2012 calendar year | Leta is setting up a mtg- then they will send it to SSC as a final report, then we can implement
25 | Complete stormwater master plan for Mathews Avenue | F&S | spring
26 | Composting Grant | F&S | 2012-01-13
27 | Composting Business Plan | F&S | spring | sent out word doc, need to set meetings | Amelia
28 | Discuss a surplus website with Property Accounting | Everyone | January | mtg with jeff weaver and cameron fear | mbj - to set
29 | Identify Local Foods Network leadership; build institutional momentum | Everyone | spring
30 | Focus on Waste diversion with Tracy Osby: review 2010 Waste Reduction Plan, Review and clarify iCAP goals, discuss possibility of expansion | Everyone | Summer 2012
31 | Battery Recycling | F&S | January | developing fact sheet and other materials | Amelia
32 | Discuss investment portfolio with the Foundation, relating to Sustainability | Everyone | spring
33 | Submit formal SSC proposal for bike parking | F&S | spring | write it… | mbj
34 | princeton review | OS | 2012-01-18 |  | SML
35 | ghg emissions | OS | 2012-01-13 | turn it in | SML
36 | sierra club survey | OS | march
37 | DCEO grant 09-466012 | F&S | 2012-01-12 | tell them how much more money we can take | SML
38 | review comments and notes from iCAP Forum | us | 2012-01-17 | read the notes | us
39 | Zipcar - marketing | F&S | spring | upcoming mtg | SML & MBJ
40
41
42
43
44

## Finished
# | Task | Staff Involved | Date Finished | Notes | Person