## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | The Mahomet Lots: Designing Sustainable Parking Lots for the University of Illinois Campus
Total Amount Requested from SSC: | 25000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
ALL ITEMS FALL WITHIN THE SPRING SEMESTER
Project start-up, pavement research conceptual/technical | 3 |  | 2017-02-02
Campus site research, pavement inventory | 2 |  | 2017-02-09
Campus site research, site selection | 1 |  | 2017-02-23
Site design, conceptual | 3 |  | 2017-03-16
Site design, design development | 4 |  | 2017-04-13
Public presentation | 1 |  | 2017-04-20
Site design,refinement | 2 |  | 2016-05-02
Presentation to administration and organizations for approval | 2 |  | 2017-05-10
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Site survey | 4500 | 1 | 4500
Geotech investigation and report | 3500 | 1 | 3500
Data collection/monitoring equipment | 6000 | 1 | 6000
|  | Subtotal | 14000
Publicity & Communication
Printed final report (10 hard copies) | 25 | 10 | 250
|  | Subtotal | 250
Personnel & Wages
Course TA (graduate or PhD student) | 4350 | 1 | 4350
Design-constructability consultant, hourly | 150 | 16 | 2400
Sustainable pavement specialist, hourly | 150 | 4 | 600
Sustainable soils specialist, hourly | 150 | 4 | 600
Illinois-Indiana Sea Grant communication specialist | 60 | 10 | 600
TA (hourly for web page development) | 20 | 20 | 400
Civil engineering student lab time | 20 | 20 | 400
|  | Subtotal | 9350
Project Budget per F&S
N/A |  |  | 0
|  | Subtotal | 0
General Supplies & Other
Display boards & hardware | 200 | 1 | 200
Plotting budget | 500 | 1 | 500
Material samples, from product manufacturers | 250 | 1 | 250
Physical site model | 450 | 1 | 450
|  | Subtotal | 1400
|  | TOTAL BUDGET | 25000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
End of Application