iCAP Transportation Team

December Meeting Minutes

12/1/2023 3:00 P.M. – 4:00 P.M.

Teams

Action Items

- Survey of all people who have a parking pass to question about EV charging

- Erin- compile info on parking permits 2018-2023 parking permits: where they were purchased (what lots), by whom (facility, staff, student), current lot capacity, ADA parking spots, number of existing EV chargers

  - Based on that, we can figure out what percentage of cars are EVs are in that lot and can assume how many EV chargers will be needed in the future

- Once data from Erin is shared...

  - Have iCAP students meet with Sarthak to analyze data

  - Interpret results

    - Will ask iCAP team to help analyze results once data is compiled

  - Draft report to parking department that outlines how the University can improve the DESMAN proposal

  - Meet with EV Task Force to discuss the report

  - Submit final report by the end of January

- Think of how we can get more people to use EV chargers on campus

- Meet the week of December 18th to discuss the next steps of the Sustainable Fleet Replacement Plan with Sarthak, Shawn, Olivia, and possibly another student

Meeting Minutes

- Introductions

  - Sarthak Prasad

  - Olivia Messerges

  - John Rubins

  - Shawn Patterson

  - Erin Kristovich

- Erin update on counting EV and hybrid cars at UIUC

  - Attempted to go through the database, but was unable to get an accurate number

  - Erin estimates between 16-377 EVs on campus

    - Lots of limitations with this data

    - EVs are no longer being required to end their license plates with “EL”

    - This throws off the data collection

  - Best way to estimate the number of EVs on campus is to send a survey to all parking permit holders

  - Erin will compile requested data and share with the team

- Sarthak met with Curbside Electric- a potential EV charging vendor

  - No cord, nothing else, just bollard all electrical and utility line are below ground

  - Focus on residential areas, not parking lots

- Update for the Sustainable Fleet Replacement Plan recommendation

  - Transportation 015 Fleet Replacement Plan was successful

  - F & S has a fleet replacement plan for F & S, but there are other fleets on campus that we don’t know much about

  - Figure out what creates a "fleet,” how many fleets there are on campus, and assign role of “Fleet Administrator”’ to each department that has a fleet (not a new position)

  - Meet the week of December 18th to discuss the next steps of the Sustainable Fleet Replacement Plan with Sarthak, Shawn, Olivia, and possibly another student