## Sheet1
UIUC 2023 Building Waste Audit Collection Schedule- Oct. 23-27 | [6 empty] | ISTC Team arrives at WTS each day at 8 AM |  |  |  | Trailer dropped off: | Fri. 10/20 2PM | Trailer picked up: First thing in the AM, Mon. 10/30
Gaylords will be placed at the buildings to be sampled first thing on Monday morning 10/23
Collection Days
Activity Zone | Building | Address | Boxes | Mon. 10/23 | Tues. 10/24 | Wed. 10/25 | Thurs. 10/26 | Friday 10/27 | Sample Pickup (ISTC) | Contact(s) | Email | Phone | Notes/Questions
Academic | Business Instructional Facility (BIF) | 515 E Gregory Dr, Champaign, IL 61820 | 1 landfill; 1 recycle. Place on the dock against railing that faces dumpster. | [5 empty] | Begin sample pick up Tuesday mid-day; pick up again on Wed. morning (& Thursday morning, if needed) | Kari Cooperider | kacoop@illinois.edu | 217-244-2929 | Zero new 3-bin branded stations; 6 older 3-bin custom stations & variety of other bins. What day/time is trash & recycling typically collected?M-F ~7 AM. Are Big Belly compactors still used on campus? No, pilot on the Quad. If not, why? Compactors--makes second sort difficult.
[10 empty] | Pete Varney (for F&S BSWs) | pvarney@illinois.edu | 217-333-7583 | BSW instructions & schedule to Pete & Daphne. BSWs service the building between 11 PM-7 AM.
Academic | Campus Instructional Facility (CIF) | 1405 Springfield Ave, Urbana, IL 61801 | 1 landfill; 1 recycle. Place next to the dumpsters outside (yellow hashed area next to dock) | [5 empty] | Begin sample pick up Tuesday mid-day; pick up again on Wed. morning (& Thursday morning, if needed) | Eric Vetter | eavetter@illinois.edu | 217-333-0534 | BSW instructions & schedule to Pete & Daphne. Also send Eric BSW instructions & schedule. What day/time is trash & recycling typically collected? M, W, F ~6 AM. 16 new 3-bin stations; tallboys in classrooms for trash, additional bins set out for events. Possible miscommunication re: purchasing customized 3 bin stations? New capital projects--encouraged to cover costs of bins. Also, if a large stock customized bins is desired, dept. covers cost. So CIF may have covered cost for both those reasons. Location of spent marker/pen collection? No, not currently, though there has been discussion of looking into a TerraCycle collection.
[10 empty] | Pete Varney (for F&S BSWs) | pvarney@illinois.edu | 217-333-7583 | BSW instructions & schedule to Pete & Daphne. BSWs service the building between 11 PM-7 AM.
Academic + Lab | Noyes Lab | 505 S Mathews Ave, Urbana, IL 61801 | 1 landfill; 1 recycle; instruct BSWs to double bag broken glass before placing into gaylord. Place next to dumpster on either side. | [5 empty] | Begin sample pick up Tuesday mid-day; pick up again on Wed. morning (& Thursday morning, if needed) | Shane Brownfield | sbrownfi@illinois.edu | 217-898-1725 | 5 new 3-bin stations; variety of older bins. How should we deal with broken glass? Recommend double bagged or boxed; include on BSW instructions. What day/time is trash & recycling typically collected? M-F, ~7-8 AM.
[10 empty] | Pete Varney (for F&S BSWs) | pvarney@illinois.edu | 217-333-7583 | BSW instructions & schedule to Pete & Daphne. BSWs service the building between 2 PM-11 PM.
Academic + Lab | Roger Adams Lab (RAL) | 600 S Mathews Ave, Urbana, IL 61801 | 1 landfill; 1 recycle; instruct BSWs to double bag broken glass before placing into gaylord. Place on small concrete pad next to large dumpster & in front of paper dumpster. | [5 empty] | Begin sample pick up Tuesday mid-day; pick up again on Wed. morning (& Thursday morning, if needed) | Shane Brownfield | sbrownfi@illinois.edu | 217-898-1725 | 3 new 3-bin stations; 4 additional requested. Variety of other bins. ISTC to collect from foam cage too; when is that picked up? Call-in basis; fills maybe once/month. That was not lined with a bag; empty during walkthrough. Since Dart is closing at end of year, this special collection is going to sunset unless F&S IDs another option. How should we deal with broken glass? Recommend double bagged or boxed; include on BSW instructions. Paper dumpster present. What day/time is trash & recycling typically collected? M, W, F, ~7:30 AM.
[10 empty] | Pete Varney (for F&S BSWs) | pvarney@illinois.edu | 217-333-7583 | BSW instructions & schedule to Pete & Daphne. BSWs service the building between 2 PM-11 PM.
Multi-Activity | Activites & Recreation Center (ARC) | 201 E Peabody Dr, Champaign, IL 61820 | 1 landfill; 1 Recycle; 1 for cardboard. Place in fenced area next to wooden steps by dumpster or just outside fenced area along the side. | [5 empty] | Begin sample pick up Monday afternoon; continue on Tuesday morning (& Wed. if needed, though highly unlikely due to generation at this building) | Jerry Watzlawick | jdwatzla@illinois.edu | 217-419-4168 | Jerry will should be our main POC for collection, send him BSW instructions & schedule. ARC coordinates own BSWs. 3 new 3-bin stations; wide variety of other bins, including older 3-bin stations. Trash dumpster emptied Tuesday ~10AM; Cardboard Dumpster emptied Wednesdays. Is other recycling also picked up on Wednesday? Yes, timing uncertain, probably before 10, ~8AM.
[10 empty] | Michael Merriman | merriman@illinois.edu | 217-649-5123
[10 empty] | Terry Elmore | telmore@illinois.edu
Multi-Activity | Illini Union | 1401 W. Green St., Urbana, IL 61801 | 1 landfill; 1 Recycle; 1 for cardboard. Place in dumpster area in west corner, against landing/white railing | [5 empty] | Begin sample pick up Monday afternoon; continue on Tuesday morning (& Wed. if needed, though highly unlikely due to generation at this building) | Wade Franklin | wfrankli@illinois.edu | 217-333-2917 | BSW instructions & schedule to Aaron Walker (cc Wade, who will be out of office 10/16-10/30). Union provides own BSWs; they service the building 5 AM to midnight. Several newer 3-bin stations; variety of other bins too. What day/time is trash & recycling typically collected? Tuesdays ~11 AM (compactor); According to Union staff, blue recycling totes in dumpster area emptied daily; the cardboard dumpster is emptied 1 or 2 times daily.
[10 empty] | Aaron Walker | amwalker@illinois.edu
Student Living | Allen Hall & Lincon Ave. Residence Hall (LAR) | AH: 1005 W. Gregory Dr., Urbana, IL 61801; LAR: 1005 S. Lincoln Ave., Urbana, IL 61801. | 1 Landfill; 1 Recycle; place at dock where temporary dumpster was | [5 empty] | Begin sample pick up Monday afternoon; continue on Tuesday morning (& Wed. if needed, though highly unlikely due to generation at this building) | Matt Brown | mmbrown8@illinois.edu | 217-300-7571 | Send BSW instructions & schedule to Matt & Mark. Housing coordinates own BSWs. Zero newer 3-bin stations. These buildings share dumpsters/recycling totes & were treated as one unit during previous audit. Ok to treat as one now. What day/time is trash & recycling typically collected? Open top emptied Mon.through Saturday (will probably be gone by audit time). Recycling picked up on same schedule, similar timing to open top dumpster.
[10 empty] | Mark Kuehl | mkeuhl@illinois.edu |  | Run any communications for student focus group participation through Mark.
ISTC will begin picking up samples from gaylords on Monday afternoon (for buildings that provide their own BSWs). Samples will be collected from each building for a minimun of 2 days or until an adequate sample of 250-300 lbs is collected. Friday should be left for completing sorting & cleaning up in the afternoon. Gaylords can be retrieved from buildings at any time once an adequate sample size has been collected.