## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Campus Lumber
Total Amount Requested from SSC: | 84581.85 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 4/26/24
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Purchase of Wood-Mizer Sawmill | 3 |  | 2024-05-22
Insatllaiton of Electrical Connections at site | 6 |  | 2024-06-26
Installation of Sawmill at site | 2 |  | 2024-07-10
Hiring of Student Workers | 4 |  | 2024-08-07
First lumber is milled | 2 |  | 2024-08-21
Lumber drying time | 8+ |  | 10/16/2024+
Lumber allocated to first project/shop | 4 |  | 2024-11-13
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Wood Mizer Saw Mill | 14894 | 1 | 14894
Electrical Installation estimate | 15000 | 1 | 15000
Replacement Blades 15pk | 400 | 6 | 2400
Power Feed for saw mill | 1325 | 1 | 1325
Log Clamp | 135.45 | 2 | 270.9
Mill Head cover | 225 | 1 | 225
Pro Package (tools to move logsonto mill) | 625 | 1 | 625
Toe boards (to level log for cutting) | 495 | 1 | 495
Resaw attachement (making veneer etc) | 3195 | 1 | 3195
LT15 stand for resaw attachment | 281.95 | 1 | 281.95
|  | Subtotal | 38711.85
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Student Worker Wages | 15 | 1440 | 21600
0
0
0
0
0
0
0
0
0
|  | Subtotal | 21600
Project Budget per F&S
Operating and Transportation | 400 | 60 | 24000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 24000
General Supplies & Other
Metal Detector (Lumber Wizard) | 150 | 1 | 150
Mini Ligno moisture meter | 120 | 1 | 120
0
0
0
0
0
0
0
0
|  | Subtotal | 270
|  | TOTAL BUDGET | 84581.85
End of Application
Note on D71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 years of wages for 1 student at $15, 10 hour per week, 36 weeks per year