## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Climate Change in your Neighborhood Project
Total Amount Requested from SSC: | 9704 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 02/13/2024
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Meeting with faculty advisors/literature review | 4 |  | 2023-12-15
Writing a standard protocol | 8 |  | 2024-02-01
Basic lab/equipment training | 1.5 |  | 2024-04-22
Data collection | 18 |  | 2024-09-01
Analysis of biodiversity index through sequencing | 8 |  | 2024-12-20
Statistical analysis of water retention, air capacity, temperature | 8 |  | 2024-12-20
Drafting a research paper | 12 |  | 2025-03-15
Submitting to research journal | 4 |  | 2025-03-15
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
ILLUMINA MISEQ V3 Sequencing | 2200 | 2 | 4400
DNeasy Powersoil Kits | 454 | 5 | 2270
Soil Sampler Probe | 20 | 2 | 40
Atmotube Sensor | 189 | 6 | 1134
Mini Disc Infiltrometer | 325 | 2 | 650
Protective Ventilated Box for Atmotubes | 30 | 4 | 120
0
|  | Subtotal | 8614
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Pipette Tips | 9 | 60 | 540
Culture Plates | 18 | 30 | 540
PVC Pipe | 10 | 1 | 10
0
0
0
0
0
0
0
|  | Subtotal | 1090
|  | TOTAL BUDGET | 9704
End of Application