## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Appropriate woodchip mulch for environmental sustainability
Total Amount Requested from SSC: | 9925 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 9/20/2023
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Materials and chemical acquisition for experiment | 6 |  | 2024-02-15
Purchase materials for laboratory setup | 6 |  | 2024-03-28
Construction of laboratory setup | 16 |  | 2024-07-18
Laboratory investigation | 32 |  | 2025-02-27
Analysis and results | 16 |  | 2025-06-19
Project dissemination/paper writing | 16 |  | 2025-10-09
92
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Scanning electron microscope use charge | 50 | 20 | 1000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 1000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Undergrad hourly (5-6 hours per week @ $15/hr) for fall 2024 & spring 2025 | 2925 | 2 | 5850
0
0
0
0
0
0
0
0
0
|  | Subtotal | 5850
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Woodchips mulch, variable sources | 50 | 10 | 500
Laboratory chemicals | 800 | 1 | 800
Pipes and fittings | 475 | 1 | 475
Water tanks, buckets, columns, supports | 800 | 1 | 800
Additives for Phosphorus filter | 500 | 1 | 500
0
0
0
0
0
|  | Subtotal | 3075
|  | TOTAL BUDGET | 9925
End of Application
Formulas:
Estimated Completion Date = [Estimated Completion Date, row above]+[Timeframe (# of weeks to completion)]*7