## Semester Project Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regarless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: |  | Ghost Electric Motorcycle
| Original Award Date (or Semester/Year)*: |  | 2024-04-19 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): |  | 9666.07
| Total Expenses This Period**: |  | 7252.84 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: |  |  | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: |  | 2025-05-20
| Date of This Application Submission: |  | 2024-12-19
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  |  | Start Date | End Date (or estimated) | % Complete
Get shop space to work on motorcycle |  |  |  | 2024-01-20 | 2024-11-08 | 100%
Receive funding to start buying parts |  |  |  | 2024-01-20 | 2024-02-12 | 100%
Get financial and educational sponsors |  |  |  | 2024-01-20 | 2024-02-12 | 100%
Get consistent engineers |  |  |  | 2024-01-20 | 2024-09-15 | 100%
Secure meeting space for logistical meetings |  |  |  | 2024-01-20 | 2024-09-16 | 100%
Dedicated executive board |  |  |  | 2024-01-20 | 2024-01-30 | 100%
Set goals for the coming semester |  |  |  | 2024-01-20 | 2025-01-20 | 70%
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item | Cost per Unit | Quantity | Total Cost
Assorted heat shrink | 8 | 1 | 8
Samsung 50S 21700 5000mAh 25A Battery Cells | 4.65 | 800 | 3720
5 piece assorted pliers set | 42 | 1 | 42
MOTO-D "RACE" STANDS (FRONT + REAR) - Tire Stand | 194 | 1 | 194
144-Position Flex-Head Ratcheting Combination Wrench Set SAE and METRIC | 449 | 1 | 449
Milwaukee® M18 FUEL™ Hammer Drill and Impact Driver Combo Set | 525 | 1 | 525
Milwaukee® Packout™ Storage System - 6-Piece Kit | 530 | 2 | 1060
Digital Caliper | 25.99 | 2 | 51.98
LCD Screen Micrometer | 195 | 1 | 195
Hammer drill and impact driver combo set battery | 195 | 1 | 195
hack saw kit including replacement blades | 23.99 | 1 | 23.99
15 in. Fatmax Stanley Hand Saw | 20.21 | 1 | 20.21
6 pc. screwdrivers with multiple tips | 28 | 1 | 28
Bondhus Metric and Standard Allen Wrench Set | 44.61 | 1 | 44.61
DeWalt 204 Piece Tools Set | 290 | 1 | 290
Utility Knives + extra blades | 27.97 | 1 | 27.97
Eastwood 4 pc. Metal File Set | 16.97 | 1 | 16.97
50 sheets of various grits | 27.17 | 1 | 27.17
Nut and bolt thread checker metric and standard | 16.98 | 1 | 16.98
Ratcheting crimping tool 10-22 AWG | 29.98 | 1 | 29.98
Box of 200 rags | 35.94 | 1 | 35.94
3 Piece Adjustable Wrench Set | 36.43 | 1 | 36.43
Countersink and Deburring Tool | 25.73 | 1 | 25.73
12 Rolls of Duct tape | 55.48 | 1 | 55.48
Hot glue gun with extra sticks | 38.97 | 1 | 38.97
5 pack Electrical tape | 21.96 | 2 | 43.92
Pack of 12 Safety Glasses | 15.95 | 1 | 15.95
Pack of 4 Safety Glasses OTG | 9.99 | 1 | 9.99
Pack of 4 Ratchet Straps Set | 24.57 | 1 | 24.57
Equipment & Construction Costs Subtotal |  |  |  |  | 7252.84
Publicity & Communication
Item |  |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  |  | 0
Personnel & Wages
Item |  |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  |  | 0
General Supplies & Other
Item |  |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  |  | 7252.84