## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illinois Solar Decathlon Build Project
Total Amount Requested from SSC: | 150000 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 5/1/24
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Apply for Building Permit | 3 |  | 2024-05-06
Design + Landscape Review | 3 |  | 2024-05-13
Utility Extension Application | 3 |  | 2024-05-15
Fire Dept Review | 1 |  | 2024-05-08
Complete Design | 1 |  | 2024-07-22
Contracting | 8 |  | 2024-09-16
Mobilization + Site work | 6 |  | 2024-11-18
Excavation | 2 |  | 2024-12-12
Foundation | 2 |  | 2025-01-16
Wall + Floor + Deck Wood Framing | 2 |  | 2025-02-20
Roofing | 1 |  | 2025-03-25
Exterior Sheathing | 2 |  | 2025-04-25
Plumbing Rough-ins | 1 |  | 2025-05-21
HVAC Rough-ins | 1 |  | 2025-06-17
Insulation | 1 |  | 2025-08-07
Drywall | 1 |  | 2025-09-03
Exterior Doors/Windows | 1 |  | 2025-09-25
Interior Doors | 1 |  | 2025-10-13
Finishes | 3 |  | 2025-10-30
Appliances | 1 |  | 2025-11-24
Substantial Completion | 15 |  | 2026-02-09
Landscaping | 3 |  | 2026-03-12
Final Inspection | 1 |  | 2026-04-03
Certificate of Occupancy | 1 |  | 2026-04-08
Move-In | 1 |  | 2026-04-23
Contingency | 80 |  | 2026-08-13
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request | Priority
Equipment & Construction Costs
Transportation (gas reimbursement to and from site) |  |  | 833.79 | Priority-3
Site Modifications and Surveying |  |  | 4500 | Priority-3
Construction Facilities (warehouse, heavy equipment, etc.) |  |  | 7847.46 | Priority-2
Permits & Utility Fees (from city, water, sewer, electric, etc.) |  |  | 5885.6 | Priority-3
Site Work (landscaping, sidewalks, utilities) |  |  | 60357 | Priority-2
Hardscape |  |  | 15942 | Priority-2
Sidewalks |  |  | 39415 | Priority-2
Utilities |  |  | 5000 | Priority-2
Foundations (excavation, concrete, formwork, etc.) |  |  | 44141.98
Excavation |  |  | 8741.06 | Priority-1
Concrete |  |  | 15300.42 | Priority-1
Formwork |  |  | 20100.5 | Priority-1
House Materials (framing, finishes, plumbing, HVAC, PVE, etc.) |  |  | 111826.35
Framing |  |  | 43289.4 | Priority-1
Insulation |  |  | 20344.5 | Priority-1
Siding |  |  | 15403.56 | Priority-1
Roofing |  |  | 12788.33 | Priority-1
Cabinetry |  |  | 20000.56 | Priority-1
Overhead & General Expenses |  |  | 16087.3 | Priority- 2
Construction Tools (handheld, lighting, construction camera, etc.) |  |  | 4904.66 | Priority-2
Construction Liability Insurance (as necessary) |  |  | 4904.66 | Priority-2
|  | Subtotal | 261288.8
Publicity & Communication
Community Exhibit Materials (signage, handouts, screens, etc.) |  |  | 2452.33 | Priority-3
Photographers/Videographer Expenses (if possible) |  |  | 980.93 | Priority-3
|  | Subtotal | 3433.26
Personnel & Wages
Professional Services (architect, structural engineer, etc.) |  |  | 4904.66 | Priority-2
House Professional Labor (required to supplement student labor) |  |  | 49046.65 | Priority-2
|  | Subtotal | 53951.31
Project Budget per F&S
We are not working with F&S. |  |  | 0
|  | Subtotal | 0
General Supplies & Other
General Supplies (code manuals, software) |  |  | 780 | Priority-2
Code manuals |  |  | 180 | Priority-2
Software |  |  | 600 | Priority-2
Competition Event cost |  |  | 5040 | Priority-3
Hotel |  |  | 2000 | Priority-3
Travel |  |  | 3040 | Priority-3
|  | Subtotal | 11640
|  | TOTAL BUDGET | 330313.37
End of Application
Note on D84: ====== ID#AAABH9srPaI Karina Jang (2024-03-20 16:38:50) should specify how many photographers/videographers and the wage (this most likely won't be able to be funded tho)