## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illini Solar Car - 4th Generation Vehicle
Total Amount Requested from SSC: | 100200
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Project Start | 0 |  | 2023-11-01
Vehicle Planning & Competitor Benchmarking | 6 |  | 2023-12-13
Shell Design | 31 |  | 2024-06-05
Chassis and Rollcage Design | 33 |  | 2024-06-19
Mold Construction | 36 |  | 2024-07-10
Suspension Design | 41 |  | 2024-08-14
Battery Box Design | 41 |  | 2024-08-14
Low Voltage Electrical System | 43 |  | 2024-08-28
Mold Machining | 43 |  | 2024-08-28
Chassis, Suspension, Rollcage Finite Element Analysis | 52 |  | 2024-10-30
Mold Pre-Processing | 54 |  | 2024-11-13
Layups | 68 |  | 2025-02-19
Mold Post-Processing | 74 |  | 2025-04-02
In House Machining & Waterjetting | 75 |  | 2025-04-09
Battery Box Assembly | 79 |  | 2025-05-07
Mate Shell and Chassis | 80 |  | 2025-05-14
Electrical System Integration | 80 |  | 2025-05-14
Vinyl Wrap and Apply Logos | 80 |  | 2025-05-14
Unveiling Event | 82 |  | 2025-05-30
Race Preparations | 88 |  | 2025-07-11
Pack Car to Ship to Australia | 91 |  | 2025-08-01
Bridgestone World Solar Challenge 2025 | 106 |  | 2025-10-30
Project Final Report | 113 |  | 2025-12-12
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
High Efficiency Silicon Solar Cells | 10000 | 1 | 10000
Solar Cell Encapsulation | 15000 | 1 | 15000
Maximum Power Point Trackers | 1000 | 3 | 3000
Foam for Shell Mold | 600 | 42 | 25200 | Find Cost
Batteries for new Battery Pack | 12000 | 1 | 12000
Mitsuba Motor and Controller | 35000 | 1 | 35000
0
0
0
|  | Subtotal | 100200
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 100200
End of Application
|  | Subtotal | 100200
|  | TOTAL BUDGET | 100200
End of Application