## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Power Station
Total Amount Requested from SSC: | 3950 | Total Amount Allocated: | 3950
Date of Submission: | 5/10/2024
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
(Completed) Design theory and parts research | 12 |  | 2024-04-15
(Completed) Initial 18650 battery test assembly | 2 |  | 2024-03-19
(Completed) Prototype system parts research and design | 2 |  | 2024-03-13
(Completed) Prototype assembly | 1 |  | 2024-03-20
(Completed) Prototype testing | 1 |  | 2024-03-23
(Completed) 18650 battery assembly [Batch-2] | 2 |  | 2024-04-06
(Completed) Order and receive Power Station parts | 2 |  | 2024-05-01
(Completed) Power Station initial test integration | 1 |  | 2024-05-10
Stress test current design | 1 |  | 2024-06-04
Assemble remaining 18650 batteries | 2 |  | 2024-10-01
Write documentation for 18650 assembly | 1 |  | 2024-10-08
Design better internal mounting for Power Station | 6 |  | 2024-10-15
Research feasibility of 24V system | 6 |  | 2024-10-15
Complete final report and other documentation (throughout) | 2 |  | 2024-12-11
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs (Current Purchases)
12V LifePO4 Battery | 970.01 | 1 | 970.01
2000W Pure Sine Wave Inverter | 275.49 | 1 | 275.49
400W Portable Solar Panels | 626.99 | 1 | 626.99
Automotive Fuses | 81.82 | 1 | 81.82
DC Regulators (9V, 12V, 5V, 3.3V) | 90.07 | 1 | 90.07
USB-C Power Delivery Charger/Port | 53.05 | 1 | 53.05
18650 Protection Circuits | 9.99 | 6 | 59.94
Battery Tester | 36.98 | 1 | 36.98
18650 Heathshrink Spool | 6.2 | 1 | 6.2
Wire and Harnessing Supplies | 235.75 | 1 | 235.75
Raw Material (Wood/Acrylic) | 151.27 | 1 | 151.27
0
|  | Subtotal | 2587.57
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 2587.57
End of Application