## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | UIUC Rainwater Management Plan
Total Amount Requested from SSC: | 200000 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 12/11/23
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Begin Capital Project, gain project approval and contract with a retainer engineer with Facilities & Services (F&S) | 1 to 2 months |  | End December 2024
Engineer to gather data and discuss issues with stakeholders | 2 months |  | End January 2024
Engineer to prepare a draft master plan and submit for owner review | 1.5 months |  | End March 2024
Engineer to respond to comments, prepare Pre-Final master plan and submit for review. | 1.5 months |  | End April 2024
Engineer to respond to comments, prepare Final master plan and submit. | 1 month |  | End June 2024
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
NA |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
Facilities & Services Customer Relations & Communications Division publicity on campus |  |  | Free
Consultant will provide a public forum on the final report |  |  | Included in consultant fee
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
NA |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Consultant fee |  |  | 175000
F&S Standards Review costs |  |  | 5000
Project Management fees |  |  | 20000
0
0
0
0
0
0
0
|  | Subtotal | 200000
General Supplies & Other
NA |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 200000
End of Application