## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | A Student-driven recensus of the Trelease Woods Forest Dynamics Plot
Total Amount Requested from SSC: | 72721.05
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Recruitment of undergraduate students | 8 |  | 2023-01-05
Training of undegrad students in census protocol | 1 |  | 2023-01-09
Census work by IB390 students | 19 weeks (early Fall and late Spring semesters) |  | 2024-01-05
Data checks by graduate Research Assistant | 48 weeks |  | 2024-07-08
Summer census work by hourly undergrad workers | 14 weeks |  | 2024-07-08
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
11 month Graduate Student Research Assistant | 32846 | 1 | 32846
Hourly paid undergraduate workers at $13 per hour x 490 hours | 6370 | 6 | 38220
0
0
0
0
0
0
0
0
|  | Subtotal | 71066
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Factory servicing/recalibration of TruPulse 360R laser rangefinders | 200 | 3 | 600
Tape inserts for Forestry suppliers 5 M diameter tape | 30 | 6 | 180
SPI Plastic dial caliper 31-413-5 to measure small trees | 44.95 | 4 | 179.8
Nelson Paint Nel-script tree marking paint | 10 | 50 | 500
Aluminium nails (1lb box) | 6.75 | 3 | 20.25
Forestry supplies vinyl tree tape (rolls) to mark small trees | 1.75 | 100 | 175
0
0
0
0
|  | Subtotal | 1655.05
|  | TOTAL BUDGET | 72721.05
End of Application