## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Improving the sustainability of the freezer room at the Wildlife Veterinary Epidemiology Laboratory.
Total Amount Requested from SSC: | 50000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Secure funding | 3 |  | 2023-05-15
Work with F&S on scheduling | 1 |  | 2023-05-22
Electrical Capacity Work | 4 |  | 2023-06-19
Air Conditioning Installation | 4 |  | 2023-07-17
Prepare Progress Update | 4 |  | 2023-08-21
Submit Final Report | 4 |  | 2023-09-18
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Increasing Electrical Capacity (2021 Estimate*) | 12397 | 1.08 | 13388.76
A/C Installation (2021 Estimate*) | 26565 | 1.08 | 28690.2
Micelaneous Expenses (unforseen changes to quote) | 8000 | 1 | 8000
* Quantity adjusted for 2 year inflation at 4% rate |  |  | 0
* See attached F&S quote for budget description |  |  | 0
0
0
0
0
|  | Subtotal | 50078.96
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 50078.96
End of Application