## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Low-cost Inspection and Sustainable Repair of Campus Pavements
Total Amount Requested from SSC: | 106000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Literature review | From week 0 to week 13 |  | 2022-12-01
Development of a software based on the AI for the image analysis and the detection of the cracks | From week 0 to week 26 |  | 2023-03-01
The mapping of the existing cracks with smartphones and drones for some sections in the campus (more damaged) and the classification of the cracks according to the maintenance priority | From week 27 to week 52 |  | 2023-09-01
Development of a special sealant for the pavement reparation | From week 53 to week 78 |  | 2023-03-01
Application and testing of the sealant agent on the predetermined sections for repair | From week 79 to week 104 |  | 2023-09-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Sealants | 2500 | 1 | 2500
Drone | 500 | 1 | 500
Cameras | 500 | 2 | 1000
0
0
0
0
0
0
0
|  | Subtotal | 4000
Publicity & Communication
Publications in scientific peer reviewed journals | 3000 | 2 | 6000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 6000
Personnel & Wages
PhD student per year | 30000 | 2 | 60000
Master student per year | 30000 | 1 | 30000
0
0
0
0
0
0
0
0
|  | Subtotal | 90000
Project Budget per F&S
Construction Services (as needed) | 5000 | NA | 5000
Updating GIS with Images of Pavements Condition | 1000 | NA | 1000
0
0
0
0
0
0
0
0
|  | Subtotal | 6000
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 106000
End of Application