## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Sustainable World Network
Total Amount Requested from SSC: | 28855
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Please see Detailed Timeline of the Project in the narrative (page 3-4) as there is text hidden in this scope and sequence figure
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
• Develop partnerships with Booker T. Washington (BTW) and Champaign High Schools • Through a James Scholar project, develop a teacher and student interview focused on issues of sustainability and what is happening locally around these issues in K-12 schools • Collect and analyze teacher and student data around sustainability interests, education, and current practices • Finalize data base of sustainability education resources • Develop initial activities for use out in K-12 classrooms | 8 weeks |  | March, 2022
• Complete teacher and student interviews • Implement elementary sustainability teaching activities and “Tree Canopy Project” with interested Champaign High Schools | 8 weeks |  | May, 2022
• Analyze teacher and student interviews; collect additional information as needed • Continue development of projects using a data informed process (revise data base, continue to identify networks) • Create resources for use in elementary and high school science methods courses • Expand partnerships with additional schools (Urbana) if possible | 8 weeks |  | August, 2022
• Finalize and use materials in Fall 2022 methods courses (elementary) • Work in both Champaign and Urbana communities • Expand James Scholar project to include additional undergraduates | 20 weeks |  | December, 2022
• Use materials in Fall 2022 methods courses (elementary and high school) • Work in both Champaign and Urbana communities • Implement James Scholar project | 20 weeks |  | May, 2023
• Finalize material for continued use in methods courses • Prepare publications and conference presentations | 12 weeks |  | August, 2023
• Use materials in Fall 2023 methods courses (elementary) • Work in both Champaign and Urbana communities • Implement revised James Scholar project as a general elective or Campus Honors course and • Develop a plan for continued implementation across the multiple university courses where the Sustainable World project is integrated. • Final report written and submitted | 20 weeks |  | December, 2023
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages. (additional budget details provide on page 6 of the narrative)
Graduate Hourly (1 graduate hourly for 180 hours per year for 2 years) | 25.73 | 360 | 9262.8
Undergraduate Hourly (4 students at 5 hours/week for 8 weeks for 2 years) | 14 | 320 | 4480
1 undergradute hourly (lead undergraduate: 10 hours/week for 8 weeks for 2 years) | 14 | 160 | 2240
0
Ggraduate Hourly fringe (7.66%) | 436 | 2 | 872
0
Teacher collaborative work stipends (10 teachers per year, 25.00 per hour, 20 hours) | 5000 | 2 | 10000
Interview stipends (20 interviews per year for 2 years) | 50 | 40 | 2000
0
0
|  | Subtotal | 28854.8
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 28854.8
End of Application