## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | An Energy Saving Demonstration for Remodeling Old Structures-Phase 2
Total Amount Requested from SSC: | 24000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Place order for 3 overhead doors | 2 |  | 2020-01-31
Installation of 3 overhead doors and weatherstripping | 12-completely weather dependant |  | 2020-05-01
Purchase and install 4 thermostats | 4 |  | 2020-01-31
Additional sealing around doors | 8 |  | 2020-03-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Large North facing door, operator and weatherstripping | 6200 | 1 | 6200
Small North facing door, operator and weatherstripping | 5100 | 1 | 5100
West facing door, operator and weatherstripping | 10500 | 1 | 10500
WI-FI programmable thermostats and accessories | 400 | 4 | 1600
0
0
0
0
0
0
|  | Subtotal | 23400
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Sealant for around door frames | 220 | 1 | 220
sealant/filler for floor under doors | 380 | 1 | 380
0
0
0
0
0
0
0
0
|  | Subtotal | 600
|  | TOTAL BUDGET | 24000
End of Application