## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Enhancing Ecosystem Services in the Southern Arboretum Woodlands: Habitat Improvement and Reusing Lumber
Total Amount Requested from SSC:
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Chainsaw Safety Training (32-hrs of OSHA-approved training; in-house) | Beginning of Undergraduate Internships; depends on COVID
Pesticide Applicator / Operator Training (8-hrs min.) | Beginning of Undergraduate Internships; depends on COVID
Herbicide treatment of invasive herbacous species | Summer, Fall, and Winter 2020 |  | Winter 2020
Herbicide treatment of woody invasive species | Summer, Fall, and Winter 2020 |  | Winter 2020
Felling, bucking, and limbing of trees | Summer, Fall, and Winter 2020 |  | Winter 2020
Labor to move and/or chip woody material | Summer, Fall, and Winter 2020 |  | Winter 2020
Mowing of open blocks and perimeters | Spring, Summer, Fall 2020 |  | Fall 2020
Planting Trees and understory species | Spring, Summer and Fall 2021 |  | Fall 2021
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Chainsaw Safety Chaps (OSHA-required PPE) | 140 | 4 | 560
Integrated Forestry Helmet System (OSHA-required PPE) | 100 | 4 | 400
Leather / Mechanic's Gloves | 12 | 8 | 96
Backpack Spayer; piston-pump style (for herbicide application) | 140 | 2 | 280
Husqvarna Chainsaw; Model 550XP Mark II | 500 | 2 | 1000
Husqvarna Chainsaw; Model 572 XP | 850 | 1 | 850
Nitrile-coated Gloves (15/pk) | 15 | 4 | 60
Herbicides, Surfactants, and Colorant (15 gallons) | 40 | 15 | 600
Chainsaw Fuel (VP-SEF 50:1; 5 gallon) | 85 | 6 | 510
Bar & Chain Oil (1 gallon) | 12 | 15 | 180
|  | Subtotal | 4536
Publicity & Communication
Website Programming / Updating (40-hrs) | 12.5 | 40 | 500
Social Media (Facebook, Instagram, Twitter, YouTube, etc.); 40-hrs | 12.5 | 40 | 500
ArcGIS Online Story Maps (80-hrs) | 12.5 | 80 | 1000
0
0
0
0
0
0
0
|  | Subtotal | 2000
Personnel & Wages
Mr. Noah Campbell, Visting Academic Professional 75% Appt. | Salary+fringe $3043/mo | 20 months | 60880
2020 Undergaduate Academic Hourly, Summer Semester (2) | 12.5 | 960 | 12000
2020 Undergraduate Academic Hourly; Fall Semester | 12.5 | 200 | 2500
2021 Undergraduate Academic Hourly; Spring Semester | 12.5 | 200 | 2500
2021 Undergraduate Academic Hourly; Summer Semester (2) | 12.5 | 960 | 12000
0
0
0
0
0
|  | Subtotal | 89880
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Contractual Custom Milling of Logs into Lumber ($100/hr) | 100 | 50 | 5000
Stickers for stacking sawn lumber to properly air dry | 0.65 | 1000 | 650
Trees |  |  | 5000
Forbs, Shrubs and Grasses |  |  | 4000
Signage |  |  | 2000
0
0
0
0
0
|  | Subtotal | 16650
|  | TOTAL BUDGET | 113066
End of Application