## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illini Formula Electric
Total Amount Requested from SSC: | 50000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
2WD Car - Competition Ready Car | 12 Weeks |  | Apr. 10, 2020
Custom Motor Controller Developed | 23 weeks |  | May. 1, 2020
AWD Prototype Developed | 10 weeks |  | Feb. 29, 2020
4WD Car - Design Freeze | 9 weeks from start, Aug. 31, 2020 |  | Nov. 1, 2020
4WD Car - Welded Chassis | 7 weeks from Design Freeze Nov. 1, 2020 |  | Dec. 18, 2020
4WD Car - Rolling Car | 6 weeks from Welded Chassis Dec. 18, 2020 |  | Jan. 31, 2021
4WD Car - Driving Car | 4 weeks from Rolling Car Jan. 31, 2021 |  | Feb. 28, 2021
4WD Car - Competition Ready Car | 6 weeks from Driving Car Feb. 28, 2021 |  | Apr. 9, 2021
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
AWD Prototype Frame Construction | 2000 | 1 | 2000
AWD Prototype Powertrain Components | 500 | 1 | 500
AWD Prototype Motor Controllers | 300 | 2 | 600
Motor Housing material and CNC costs | 700 | 4 | 2800
4WD Custom motor controller parts and manufacturing | 2500 | 4 | 10000
Manufacturing for Custom Motor Gearboxes | 1200 | 4 | 4800
Chassis Tube Chassis Manufacturing Costs | 3500 | 1 | 3500
0
0
0
0
|  | Subtotal | 24200
Publicity & Communication
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Motor Dynomometer | 5000 | 1 | 5000
Battery cells for 4WD Vehicle Battery Pack | 77 | 144 | 11088
AWD Prototype Batteries | 250 | 2 | 500
AWD Prototype Motors | 200 | 4 | 800
Motors for 4WD Electric Vehicle | 1500 | 4 | 6000
10" Wheels for 4WD Electric Vehicle | 300 | 8 | 2400
0
0
0
0
|  | Subtotal | 25788
|  | TOTAL BUDGET | 49988
End of Application