## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illini Solar Car Second Gen. Vehicle
Total Amount Requested from SSC: | 40000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Aero Shell Design | 1 |  | 2018-11-09
Mechanical Design | 8 |  | 2019-01-09
Solar Array Shipment | 20 |  | 2019-05-09
Car build - Carbon Fiber layups | 16 |  | 2019-04-09
Machine Milling | 6 |  | 2018-12-23
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Mitsuba Motors | 24078.95 | 2 | 48157.9
Topfilm | 16.8 | 52 | 873.6
GH Craft Wheel Rims | 10695.15 | 1 | 10695.15
APW - foam molds cnc routing | 4400 | 1 | 4400
Scientific equipment & lab supplies | 3136.95 | 1 | 3136.95
HomeDepot (Linview Location Setup) | 966.81 | 1 | 966.81
Office equipment | 2525.39 | 1 | 2525.39
Equipment in Progress | 1730.39 | 1 | 1730.39
American Durafilm (Teflon FEP film) | 764.25 | 1 | 764.25
0
|  | Subtotal | 73250.44
Publicity & Communication
t-shirt | 8.26 | 69 | 569.94
WSC T shirt | 546.47 | 1 | 546.47
quad day registration | 28 | 1 | 28
Quad Day Fundraiser - Expenditure | 29 | 1 | 29
other t-shirt | 10 | 23 | 230
0
0
0
0
0
|  | Subtotal | 1403.41
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Rent at Linview | 14400 | 1 | 14400
Comcast (internet) | 199 | 12 | 2388
0
0
0
0
0
0
0
0
|  | Subtotal | 16788
General Supplies & Other
Shipping - Australia | 13257.13 | 1 | 13257.13
WSC Adventure Class Entrance Fee | 7691.27 | 1 | 7691.27
ASC Entrance Fee | 2556.85 | 1 | 2556.85
WSC Shipping Insurance | 750 | 1 | 750
0
0
0
0
0
0
|  | Subtotal | 24255.25
|  | TOTAL BUDGET | 115697.1
End of Application