## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu.The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
| Project Title: |  | Membrane-Based Removal of Water from Oil
| Total Amount Requested from SSC: |  | 9870.4
| Amount Requested as: |  | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
| Task |  | Timeframe (# of weeks to completion) |  | Estimated Completion Date
| Gather Equipment |  | 3 |  | End of January 2020
| Assemble System Prototype |  | 3 |  | End February 2020
| Preliminary Water Testing and System Adjustment |  | 6 |  | End of March 2020
| Oil Testing- Olive Oil |  | 9 |  | End of September 2020
| Various Oil Tests |  | 9 |  | Late December 2020/Early January 2021
| Biodiesel Tests |  | 9 |  | 2021-04-01
| Submission of Final Report |  | 9 |  | 2021-05-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
| Item |  | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
https://www.coleparmer.com/c/complete-pump-systems?N=1110848331+1668307101+1282169511+2934085933+2616779418&Ne=3328643986&Ns=P_ItemSortCPVH%7C1&format=json&rgn=P_ISUUSA&rlg=en-US&uty=dflt | Peristalitic Pumps |  | 2000 | 1 | 2000
https://www.3m.com/3M/en_US/company-us/all-3m-products/~/All-3M-Products/?N=5002385+3290344668&preselect=8710655+8758377+8759203+3292695512+3294857497&rt=rud | Membrane Modules - Liquicell |  | 500 | 3 | 1500
https://www.medpluspro.com/diacap-polysulfone-dialyzers.html?gclid=CjwKCAiA8K7uBRBBEiwACOm4d7sPwbOWdwjnilwPBBpVlPIJa3sGrg6IT1oCFEbbHLPjH6z6x1-uJxoC_EsQAvD_BwE | Membrane Modules - Dialysis |  | 20 | 10 | 200
https://www.vernier.com/products/interfaces/labq2/hardware/ | Vernier Labquest |  | 320 | 1 | 320
https://www.vernier.com/products/sensors/ph-sensors/ph-bta/ | pH Probe - Vernier |  | 79 | 1 | 79
https://www.vernier.com/products/sensors/drop-counters/vdc-btd/ | Drop Counter |  | 99 | 1 | 99
| Mounting Equipment and Assembly |  | 200 | 1 | 200
https://pvcpipesupplies.com/f-450n-1-10-gpm-75-m-npt-inline-f-45750l-12.html?gclid=CjwKCAiA8K7uBRBBEiwACOm4d_Rxri2hnVt1RpW_gJp585s8GFPzdap4ZtDvBhoEWGdj06m3fCHEvhoCOHcQAvD_BwE | In Line Flowmeter |  | 90 | 4 | 360
0
|  |  |  | Subtotal | 4758
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  |  |  | Subtotal | 0
Personnel & Wages
| Student Wages - $11 per hour/student - Over 3 Semesters |  | 22 | 192 | 4224
0
0
0
0
0
0
0
0
0
|  |  |  | Subtotal | 4224
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  |  |  | Subtotal | 0
General Supplies & Other
| Various Oils (per gallon price) |  | 32 | 7 | 224
| Tubing- Peristaltic |  | 15 | 3 | 45
| Connectors (clips, hose barbs) |  | 5 | 20 | 100
| Chemicals |  |  |  | 0
|  | Sodium Hydroxide (1 kg) | 94.5 | 1 | 94.5
|  | Toluene (1L) | 63 | 1 | 63
|  | Ethanol (1L) | 124 | 1 | 124
|  | Phenolphtalein (100g) | 21.7 | 1 | 21.7
|  | Hexane (1L) | 101 | 1 | 101
|  | Variety of Free Fatty Acids (1kg) | 65.2 | 1 | 65.2
| General Tools (Screwdrivers, Boxcutters/Knives) |  | 10 | 5 | 50
0
0
0
0
|  |  |  | Subtotal | 888.4
|  |  |  | TOTAL BUDGET | 9870.4
End of Application