## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Reusable Foodware Containers
Total Amount Requested from SSC: | 10000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Identify and ask local restaurants to participate in the program | 8 |  | 2020-06-05
Follow-up with container vendor for updated options and prices | 3 |  | 2020-05-01
Use the summer to plan for fall semester roll-out/Launch pilot program | 14 |  | 2020-08-21
ex. design and branding
ex. product purchasing
ex. marketing prep
Semesterly Report |  |  | January, 2021
Final Report (after full school year) |  |  | Summer 2022
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
Marketing & Education | 1500 | 1 | 1500
Program Branding (labels, stickers, signs, etc.) | 500 | 1 | 500
0
0
0
0
0
0
0
0
|  | Subtotal | 2000
Personnel & Wages
Part-Time Student Intern (wages + fringe) | 3000 | 1 | 3000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 3000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Materials and Supplies | 4000 | 1 | 4000
ex. reusable containers |  |  | 0
ex. storage bins/trays |  |  | 0
0
0
0
0
Other Services | 1000 | 1 | 1000
0
0
|  | Subtotal | 5000
|  | TOTAL BUDGET | 10000
End of Application