## Illinois Organic Internship
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illinois Organic Intership
Total Amount Requested from SSC: | 42800
Amount Requested as: | 42800 | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Student recruitment on start date --Aug 15/2020 | 4 weeks |  | Sep 15/2020
Student training | 4 weeks |  | Nov30/2020
Independent student project design and experimental set up | 4-6 weeks |  | Mar 15/2021
Experimentation, data collection, and outreach | 15 weeks |  | Sep 15/2021
Preliminary results and presentation | 6 weeks |  | Nov 30/2021
Abstract preparation and submission to scientific conference | 2 weeks |  | Feb 15/2022
Additional supportive data collection | 8 weeks |  | May 15/2022
Poster preparation and presentation at a scientific conference | 3 weeks |  | Summer 2022
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
Posters printing for presentations | 200 | 4 | 800
0
0
0
0
0
0
0
0
0
|  | Subtotal | 800
Personnel & Wages
Student Wages for 4 students and 700 hrs/student over 2 years | 15 | 2800 | 42000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 42000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 42800
End of Application