## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Production of Safe Leafy Greens via Hydroponics by Recycling of Wastewater Nutrients
Total Amount Requested from SSC: | 10000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Order materials and assemble racks; create experimental design | 8 weeks: January2020-March2020 |  | March 2020
Grow 3 cycles of lettuce (6 weeks each) | 20 weeks: March-June 2020 |  | June 2020
Present preliminary findings and successes at Engineering Open House/Explore ACES | 2 weeks: March2020 |  | March 2020
Prepare proposals for continued funding (UIUC ACES FIRE; EPA P3; UIUC SSC Phase 2) | 24 weeks: March-August 2020 |  | August 2020
Continue growth cycles, considering new crops based on previous results | 20 weeks: August-December2020 |  | December 2020
Host campus/community demonstration at ABE instructional facility | 8 weeks: September-October 2020 |  | October 2020
Laboratory analysis of food quality to assess viability in campus dining | 24 weeks: November2020-May2021 |  | May 2021
Engage in conversations with campus dining about food production, based on results | 20 weeks: April-August 2021 |  | July 2021
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Hydroponics system (racks, buckets, lights, timers, power strips, etc.) | 700 | 5 | 3500
Fertilizer ingredients | 250 | 1 | 250
Plant seedling/plug-ins (5 racks with 3 shelves with 18 plants each = 270 per cycle) | 7.5 | 200 | 1500
0
0
0
0
0
0
0
|  | Subtotal | 5250
Publicity & Communication
Promotional and publicity materials | 250 | 1 | 250
0
0
0
0
0
0
0
0
0
|  | Subtotal | 250
Personnel & Wages
Student wages ($ per hour) | 10 | 300 | 3000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 3000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Laboratory Analysis (~$ per sample) | 15 | 100 | 1500
0
0
0
0
0
0
0
0
0
|  | Subtotal | 1500
|  | TOTAL BUDGET | 10000
End of Application