## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Bee Research Facility Sustainable Auxiliary Building
Total Amount Requested from SSC: | 220000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Finalize design | 6-8 weeks |  | 2019-08-01
Development of scope and pricing | 2-3 weeks |  | 2019-08-22
Pricing approval, project approval, submittals and bonds | 1-2 weeks |  | 2019-09-05
Construction | 10-12 weeks |  | 2020-05-01
Final report | 52 weeks |  | 2021-05-01
Note on the Final Report: In order to report on the impact of the Sustainable Auxiliary Building on both summer and overwintering projects the Final Report would be completed after the first winter of use (2020-2021). This estimated completion data could be adjusted at the Student Sustainability Committee's discretion.
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
See Project Budget per F&S |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
We are not requesting any funding for publicity or communication. In addition to the informal and organized events and tours at the Bee Research Facility which will feature the Sustainable Auxiliary Building, other forms of publicity and outreach outlined in the proposal will be supported by other means. |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
We are not requesting any funding for personnel or wages. The position of Bee Research Facility Manager is already fully supported. The oversite of the Sustainable Auxiliary Building would be the responsibility of the Bee Research Facility Manager. |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Building design | 10000 | 1 | 10000
Building construction (including infrastructure for solar panels) | 160000 | 1 | 160000
Solar panels and installation | 30000 | 1 | 30000
10% construction contingency | 20000 | 1 | 20000
We worked with Kristine Chalifoux, F&S Management Engineer, and Joshua Rubin, F&S Construction Superintendent, to generate these estimated costs. If necessary, the funding for the installation of the solar panels could be deferred to a later funding cycle. |  |  | 0
0
0
0
0
0
|  | Subtotal | 220000
General Supplies & Other
All research equipment relating to the automated behavioral monitoring system, renovation of Bee Dome flight enclosures and preliminary electrical work, estimated at $67,000, would be paid for through an ongoing external grant to the Robinson Lab from the Department of Defense - DARPA program. |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 220000
End of Application