## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Media Commons Video Production Studio Lighting Replacement
Total Amount Requested from SSC: | 5600
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Start of Project |  |  | Mid Dec (based on announcement)
Purchase of Lighting Equipment | 1 |  | 2019-01-01
Install of Lighting Equipment | 1 |  | 2019-01-14
Digital Signage and Social Media Marketing | 1 |  | Start of Spring Semester 2019
Final Report | 1 |  | End of Spring 2019 (depending on stats required)
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Dracast LED1000 Plus Series Bi-Color LED Light | 649 | 8 | 5192
Impact Pipe Clamp with Baby Pin | 46.95 | 8 | 375.6
0
0
0
0
0
0
0
0
|  | Subtotal | 5567.6
Publicity & Communication
Media Commons and Library Digital Signage | 0 |  | 0
MC and Library Social Media Accounts | 0 |  | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
n/a |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
n/a |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
n/a |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 5567.6
End of Application