## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Large scale implementation of E2E Paradigm for Food Waste to Biofuel and Biomaterial
Total Amount Requested from SSC: | 150000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Establish pretreatment methods | 8 weeks |  | January, 2019 - March, 2019
Upgrade the system to operate with this feedftock | 8 weeks |  | March, 2019 - May, 2019
Convert food waste with the system | First run period -- 8 weeks, continuely run after that |  | May, 2019 - October, 2020
Test oil yeild and quality | First test -- 8 weeks, continuely test after that |  | July, 2019 - October, 2020
Economic analysis of the system | 16 weeks |  | September, 2019 - January, 2020
Upgrading of the bio-crude oil and bio-material | Method investigation -- 8 weeks, continuely after that |  | September, 2019 - November, 2020
Implementaion of product for campus use | 24 weeks |  | May, 2020 - December, 2020
Final report write up | 12 weeks |  | August, 2020 - December, 2020
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Equipment rental (including HTL pilot reactor, and water) | 24000 | 1 | 24000
HTL system renovation (back pressure controls, trailer) | 25000 | 1 | 25000
0
0
0
0
0
0
0
0
|  | Subtotal | 49000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Graduate students | 15 | 2000 | 30000
Undergraduate students (including webmaster) | 10 | 2000 | 20000
0
0
0
0
0
0
0
0
|  | Subtotal | 50000
Project Budget per F&S
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Laboratory testing | 18000 | 1 | 18000
Supplies (feedstocks characterization) | 8000 | 1 | 8000
Biocrude upgrading | 18000 |  | 18000
Miscillaneous | 7000 | 1 | 7000
0
0
0
0
0
0
0
|  | Subtotal | 51000
|  | TOTAL BUDGET | 150000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
The PI has Obtained a Conference grant from NSF INFEWS program ($50,000) to hold a Workshop June 13-15, 2018. 2) NSF US-China INFEWS: An Integrated Technology-Environment-Economic Modeling Platform for FEW Systems in Arid Regions (PI: Cai, Co-PIs: Zhang and Davidson. $500,000, 2018-2022). PI Zhang submitted a proposal (total $2.5 million, pending) to NSF INFEWS Program Track #2 on Sept 26, 2018. The PI has ing a proposal (total $2.5 million) for the INFEWS Program Track #2.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
The pilot HTL reactor is capable of processing two ton of wetwaste (20% solids), with a carbon capture efficiency of 70%, which convert 130 kg of carbon in the biowaste into a carbon neutral biocrude oil . This capacity will translate into a reduction of 426 kg/day, or 156 ton per year, of carbon dioxide emission.
End of Application