## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | WaggleNet
Total Amount Requested from SSC: | 15000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Construct and verify mesh network technology | 8 |  | 2019-04-01
Build data collection nodes with a user-friendly package | 4 |  | 2019-05-01
Create accompanying mobile & computer applications | 12 |  | 2019-05-01
Create sensor design guide for students to build their own sensors | 4 |  | 2019-08-01
Deploy and Maintain WaggleNet devices at research partners at UIUC | 8 |  | 2019-05-01
Release trial WaggleNet devices to General Public as donation | 8 |  | 2019-05-01
Organize and execute student activities on IoT technology | 8 |  | 2019-10-01
Develop models for detecting bee diseases and swarming | 12 |  | 2019-09-01
Develop data analytics platform for sharing data with researchers | 3 |  | 2019-07-01
Develop platform for researchers to share results with users | 12 |  | 2020-01-01
Final Report |  |  | 2020-03-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Hardware development and testing equipment | 1500 | 1 | 1500
Data collecting equipment for Data Science research | 2000 | 1 | 2000
Computer hardware for Training AI models & software testing | 4000 | 1 | 4000
Electronic parts for assembling WaggleNet devices | 1500 | 1 | 1500
Software licenses for development and verifications | 1000 | 1 | 1000
0
0
0
0
0
|  | Subtotal | 10000
Publicity & Communication
Squarespace subscription for Official Website | 300 | 1 | 300
Publicity Material for Participations in Events (e.g. Posters) | 200 | 1 | 200
0
0
0
0
0
0
0
0
|  | Subtotal | 500
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
AWS@Illinois Cloud Computing Fee per year | 2000 | 1 | 2000
PCB Manufacturing and Assembly fee | 1500 | 1 | 1500
Usage of ECE Illinois Machine Shop | 200 | 1 | 200
0
0
0
0
0
0
0
|  | Subtotal | 3700
General Supplies & Other
Mechanical hardware tools (e.g. Scissors, pliers) | 200 | 1 | 200
Consumable electronic parts (e.g. wires, breadboards) | 300 | 1 | 300
Storage media for distributing data (e.g. Portable hard drives) | 300 | 1 | 300
0
0
0
0
0
0
0
|  | Subtotal | 800
|  | TOTAL BUDGET | 15000
End of Application