## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Waste to 3D production
Total Amount Requested from SSC: | 9250
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Acquisition of Hardware | 12 |  | March 1st, 2019
Installation and Testing of Machinery | 4 |  | April 10th
Beta testing with Architectural Seminar and Design Courses | 6 |  | May 25th
Workshop Open to Student Body | 2 |  | August 28th
Student Prototyping | 6 |  | July 15th
Continued Development | 8 |  | September 1st
Fabrication of Pieces to be Displayed in TBH Gallery and/or Link Gallery | 4 |  | October 1st
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Clay Printing extruder kit (3D potter) | 700 | 1 | 700
Extruder Kits | 1250 | 1 | 1250
DIY printer | 500 | 1 | 500
Air Compressor | 500 | 1 | 500
Dust collector | 400 | 1 | 400
Filastruder | 300 | 1 | 300
Stepper Motor | 50 | 1 | 50
Peripherals | 700 | 1 | 700
Modified Printer for Sawdust | 900 | 1 | 900
0
|  | Subtotal | 5300
Publicity & Communication
Material for prototypes | 600 | 1 | 600
Gallery Exhibition Production | 500 | 1 | 500
Materials for Workshops | 250 | 1 | 250
0
0
0
0
0
0
0
|  | Subtotal | 1350
Personnel & Wages
Student Labour | 1000 | 2 | 2000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 2000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Epoxy Resin | 400 | 1 | 400
UF Glue | 200 | 1 | 200
0
0
0
0
0
0
0
0
|  | Subtotal | 600
|  | TOTAL BUDGET | 9250
End of Application