## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illini Solar Car, Project Brizo
Total Amount Requested from SSC: | 10000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Project Start | n/a |  | Since February 2018
Complete Chassis Assembly | 0 |  | October 31st, 2020
Complete Suspension | 1 |  | November 15th, 2020
Complete Rolling Chassis | 2 |  | November 30th, 2020
Complete Battery Box Assembly | 2 |  | November 30th, 2020
Vehicle Integration | 7 |  | December 31st, 2020
Solar Array Adhesion | 12 |  | January 31st, 2021
Begin Vehicle Testing | 14 |  | 2021-02-01
Public Unveiling | 14 |  | 2021-02-01
Begin Race Preparations for 2021 American Solar Challenge | 16 |  | 2021-03-01
American Solar Challenge 2021 | 37 |  | July 27th - August 7th, 2021
Budget*
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
*Please see Appendix A of the proposal for a detailed breakdown of the funds requested.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Tires | 250 | 12 | 3000
Electrical Components | 3000 | 1 | 3000
Mechanical Parts | 4000 | 1 | 4000
0
0
0
0
0
0
0
|  | Subtotal | 10000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 10000
End of Application