## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: |  | Bevier Hall Occupancy Sensors
Total Amount Requested from SSC: |  | 17500
Amount Requested as: |  | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task |  | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Professional Services Consultant Amendment |  | 16 weeks |  | 2018-05-01
Request for Proposal |  | 16 weeks |  | 2018-10-01
Change order processing |  | 8 weeks |  | 2018-12-01
Construction (coordinated with other work) |  | 60 weeks |  | 2019-02-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item |  | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Occupancy Sensors |  | 1873.21 | 1 | 1873.21
Extra sensors (attic stock) |  | 200 | 0 | 0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 1873.21
Publicity & Communication
New signage at renovated rooms |  | 254.8 | 1 | 254.8
0
0
0
0
0
0
0
0
|  |  | Subtotal | 254.8
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
Project Budget per F&S
Install new occupancy sensors |  | 3892.96 | 1 | 3892.96
Modify control system |  | 8676.93 | 1 | 8676.93
0
0
0
0
0
0
0
0
|  |  | Subtotal | 12569.89
General Supplies & Other
Contingency |  | 1500 | 1 | 0
Professional Services Consultant aamendment |  | 4000 | 1 | 0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | TOTAL BUDGET | 14697.9
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Other funding comes from Deferred Maintenance, and includes $3,050,000 for the overall poject.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
|  | Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
|  | Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
We estimate that the sensors will reduce heating, cooling, and electrical energy by approximately 10% in the spaces affected, which will equal 18.69 klb of steam, 11.49 MBTU of chilled water, and 2215 kWh of electricity. This would amount to 9942 CO2lb reduction and an annual savings of $730.
End of Application
| Steam MBTU | ChW MBTU
| 11.8 | 5.63
| 2889.82 | 814.098 | 3703.918