## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Environment-friendly phosphorus filter from fly ash
Total Amount Requested from SSC: | 8350
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Obtain materials (fly ash, lime, clay, additives) | 4 |  | 2016-09-15
Experiments to improve fly ash pellet formulation | 12 |  | 2017-12-15
Purchase materials to set up pilot scale lab experiment | 4 |  | 2018-02-15
Evaluate the improved pellet product in the lab testing | 12 |  | 2018-05-15
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Pelletizer (Illinois Sustainable Technology Center) use charge | 100 | 5 | 500
ICP-MS analysis at the Chemistry laboratory | 10 | 50 | 500
Scanning electron microscope (Micro and Nano Technology Lab) use charge | 50 | 10 | 500
0
0
0
0
0
0
0
|  | Subtotal | 1500
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Undergrad hourly (10 hours/week @ $10/hr for Fall 2017 and Spring 2018) | 2800 | 2 | 5600
0
0
0
0
0
0
0
0
0
|  | Subtotal | 5600
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Lime & clay and other additives | 250 | 1 | 250
Other additives and chemical | 500 | 1 | 500
Pipes and fittings | 500 | 1 | 500
0
0
0
0
0
0
0
|  | Subtotal | 1250
|  | TOTAL BUDGET | 8350
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Fly ash to be used in the project will be provided by Abbott power plant as in-kind support). Please see attached letter of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
Not applicable since the project is not related to greenhouse gas emission.
End of Application