## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Sustainable Agricultural Food System – Juice Processing
Total Amount Requested from SSC: | 300000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Procure Phase 1 & Phase 2 Equipment | 9 months |  | Dec. 2017
Receive Phase 1 Equipment & Install | 3 months |  | Jul. 2017
Recipe development & small batches for Dining | 6 months |  | Dec. 2017
Receive Phase 2 Equipment & Install | 2 months |  | Feb. 2018
Certify full process line for pilot-scale production | 4 months |  | Jun. 2018
Begin full-scale production for Dining | N/A |  | Jul. 2018
Repeat process of planting, processing, and improving… |  |  | ongoing….
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Phase 1 | 95000 | 1 | 95000
Currant Storage Treatment and Containers ($5000) |  |  | 0
Juice Extraction ($90,000) |  |  | 0
0
Phase 2 | 205000 | 1 | 205000
Pasteurization ($100,000) |  |  | 0
Bottle Filling ($105,000) |  |  | 0
0
Dining Funded ($50,000) | 0 | 1 | 0
Mechanical Harvester |  |  | 0
|  | Subtotal | 300000
Publicity & Communication
Costs of Marketing project at UIUC Dining Service (Dining Halls) is covered |  |  | 0
covered by UIUC Dining Services. Other online marketing |  |  | 0
planned does not have associated costs. Planned tours |  |  | 0
and printed article distribution will be included with |  |  | 0
other activities already covered by FSHN. |  |  | 0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Costs of student internships and other labor |  |  | 0
covered by Dining Services |  |  | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
N/A - All equipment to be installed in FSHN Pilot Plant, a |  |  | 0
plug and play facility. |  |  | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 300000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
UIUC Dining Services has committed $50,000 to this project
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
It would be difficult to calculate an exact savings without having extensive knowledge of the current supplier's supply chains, but it is apparent the GHG savings from the reduction in gasoline use will be substantial. The juice produced on campus will travel no more than 5 miles from farm to consumption, compared with hundreds or thousands of miles with the current suppliers.
End of Application