## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | High-Resolution Temperature Profiling and Thermal Analysis for Geothermal Energy Alternatives
Total Amount Requested from SSC: | 62325
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Order and purchase field supplies and cables | 8 |  | 2016-09-30
Initiation of webpage or mobile app development | 1 |  | 2016-09-30
Installation of FO-DTS with geothermal heat exchanger | 1 |  | 2016-10-15
Drilling, core recovery/description, downhole geophysics | 2 |  | 2016-10-31
Installation of FO-DTS with geothermal heat exchanger | 4 |  | 2016-11-30
Field geothermal exchange test and thermal property test | 8 |  | 2016-12-31
FO-DTS measurement and calibration | 40 and continued |  | 2016-07-31
Optimal cost analysis of loop design and installation | 8 |  | 2016-04-30
Beta test on webpage or app development | 2 |  | 2016-03-30
Online test of webpage or apps | 2 |  | 2016-06-30
Conclude study and submit final report | 8 |  | 2016-07-31
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
DTS enclosure and mounting hardware | 720 | 1 | 720
Solar panel, battery, and hardware | 875 | 1 | 875
Cellular modem and accessories | 960 | 1 | 960
DTS Wi-Fi module and accessories | 200 | 1 | 200
Drilling rate per day | 2950 | 5 | 14750
Heat-exchange loop and FO cable installation per day | 2950 | 2 | 5900
Geophysical logging per meter | 16.5 | 100 | 1650
FO Cable and Clips from UW Geolab | 1500 | 1 | 1500
0
0
|  | Subtotal | 26555
Publicity & Communication
Cellular data communication | 52 | 10 | 520
0
0
0
0
0
0
0
0
0
|  | Subtotal | 520
Personnel & Wages
UIUC student hourly in engineering or science | 15 | 640 | 9600
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 9600
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
UIUC core sample transfer and joint analysis at UW-M | 300 | 6 | 1800
UW GeoLab: Thermal Property Tests | 1250 | 5 | 6250
UW EPD: In-situ Thermal Response Test at UIUC | 3500 | 2 | 7000
UW EPD: Assisting FO Network Setup at UIUC | 1000 | 1 | 1000
UW EPD: Review and Analysis by James Tinjum | 200 | 40 | 8000
UW WGNHS: Review by David Hart | 200 | 8 | 1600
0
0
0
0
|  | Subtotal | 25650
|  | TOTAL BUDGET | 62325
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
The service time of the team members at the ISGS and the UIUC Energy Farm will be in kind. Support letters are attached.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled water: 144.6 CO2lb/mmbtu
In the proposed project, we will collect data over an entire calendar year to identify the impacts of seasonal heating and cooling on the subsurface. The outcomes can be used to evaluate the geothermal energy contribution for future energy planning on campus.
End of Application