## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Skip The Bag
Total Amount Requested from SSC: | 64260
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Create Design for Bag | Start Date: 4/11/16. 4 weeks to completion |  | 2016-05-06
Work with Introductory courses to implement lesson plan | Start Date: 4/19/16. 9 weeks to completion |  | 2016-06-15
Order Bags | Start Date: 5/1/16. 10 weeks to completion |  | 2016-07-01
Switch from Plastic to Reusable Bags at the Illini Union Bookstore | This will start the day reusable bags are received |  | 2016-08-15
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Reusable Bags (including shipping) | 1.19 | 50000 | 59500
Tax (assumed rate of 8%) | 0.0952 | 50000 | 4760
0
0
0
0
0
0
0
0
|  | Subtotal | 64260
|  | TOTAL BUDGET | 64260
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: | Diesel:
| Steam: | Gasoline:
| Chilled Water:N/A CO2lb/mmbtu: 1.33 Tons | Oil: 250 gallons
End of Application